1-general scope and definitions

  - Definitions

    - COMPANY

    - CONTRACTOR

    - Project

    - Inspector

      - Company Inspection

      - Contractor  Inspection

      - Third Party Inspection

    - Shall

    - Should

    - Could

    - Mechanical Completion Certificate (MCC)

    - Performance Tests.

    - Provisional Acceptance Certificate (PAC)

  - Scope

  - Engineering

  - Procurement

    - Purchasing

    - Expediting

  - Delivery and transportation

  - Construction

  - Contract schedule

  - Pre-commissioning

  - Commissioning

  - Documentation

  - Warranty/guarantee

  - CONTRACTOR services

    - Scope of work

    - Spare Parts

    - Special Tools and Testing Equipment

  - Contractor’s on-site Facilities and Services

## First Aid

## Security

## Sanitation

## Project Signboards

## Vendors/Manufacturer Representative(s)

## On-site offices for Company's Staff

  - Company's Staff Training

  - Drawings

  - Discrepancies

1-General Scope and Definitions

  - Definitions

The Contractor's scope of work includes, but not limited to, the engineering, procurement, personnel, supervision, inspection, materials, consumable, transportation, construction , pre-commissioning, commissioning and start up  the PROJECT for the successful execution and timely completion with the all safety and operation requirement of the” ARAB GAS PIPELINE PROJECT- PHASE  II ” For Syrian Gas Company.

Within this contract the following definition shall be applied:

    - COMPANY

The COMPANY means when this word used the:

Syrian Gas Company or its authorized representatives performing work on behalf of Syrian Gas Company.

    - CONTRACTOR

The CONTRACTOR, if any, selected by the COMPANY to perform all the work of PROJECT and provide all the Equipment/Materials and Services as described in this RFQ and Scope of Work.

    - PROJECT

The PROJECT means when this word used the:

“ARAB GAS PIPE LINE PROJECT- PHASE II “Is defined as engineering, procurement, construction for all disciplines and activities which include but not limited to: Pipeline Installation , Four Block Valve Stations Installation , One Fiscal Metering Station ( FMS ) and Compressor units, intermediate station and all required activities but not limited to: Survey, Soil Investigation, Civil, Structural, Mechanical, Instrumentation, Electrical, Control, Telecommunication, Cathodic Protection ,Pre-commissioning ,Commissioning , Start-up Activities and Utility Systems …etc in addition to any activity required to make the system function based on the Turn key job basis.

The CONTRACTOR is Responsible to Provide All Equipment, Materials, Tools, Consumable, Transportation, Special Tools, Spare Parts, Carnage, Personnel, Supervision, Inspection, Testing etc... Necessary to Complete the PROJECT in Accordance with RFQ Specifications and International Codes and Standards

The PROJECT included but not limited to the following shown in drawing 6000-10-01:

- Installing approximately 186 km of “36”API 5L X70 pipeline between ALforeqls area and the Aleppo PRMS.

- Four (4) Block Valve Stations tagged as follow:

- BVS 6013: ref to drawing 6000-10-02

- BVS 6014: ref to drawing 6000-10-02

- BVS 6016: ref to drawing 6000-10-02

- BVS 6017: ref to drawing 6000-10-02

- Launcher at Al Foreqls area tagged L6011 at the BVS-6011  of Arab gas pipe line Phase I : ref to drawing 6000-10-03 ,and drawing D-91/2005-AB-10-002.14.

- Receiver at the Aleppo PRMS tagged R6018: ref to drawing 6000-10-04, and drawing AG70-DWG-A-PR-017.

- Launcher at Intermediate Station tagged L6015: ref to drawing 6000-10-05.

- Receiver at Intermediate Station tagged R6015: ref to drawing 6000-10-05.

- Fiscal Metering Station ( FMS ) at Al Foreqls area with 4 BCM capacity:

ref to drawing 6000-10-07

- Three gas compressor units to be installed at Al Foreqls FMS, each compressor shall operate on  50% Max Flow  rate(4 BCM) .Contractor has to design the GCS on bases  of tow compressors in operation and one stand by.

- Four  Tie-In :

-with ARAB GAS PIPELINE PROJECT - PHASE I  36” flange. at  BVS-6011.

-with ARAB GAS PIPELINE PROJECT - PHASE II-PART I  36” flange. at R-7003.

-with 36" inlet/outlet of the FMS & gas compressor.

With all related piping, materials, equipment, instrumentation, electrical, control and telecommunication systems, mechanical, civil and cathodic protection system, in addition to all auxiliary and utility systems like potable water, sewer, etc.To be handed over to the COMPANY safe and operable PROJECT as per these RFQ contained in this tender and international codes, standards and specification.

    - inspector

      - COMPANY Inspection

The inspector(any person authorized to act on owner’s behalf for all maters related for Quality Control, Testing and Acceptance of the Work described in the Scope of Work ).

Inspectors shall at all times have access to the construction or fabrication or test work wherever it is in preparation or in progress.

They will have the right to reject materials or workmanship, which are defective and require correction.

Rejected workmanship or materials supplied, constructed, tested or executed by the CONTRACTOR shall be satisfactorily corrected without any time or cost impact to the COMPANY.

inspector will decide any questions which may arise as to the quality and acceptability of construction or fabrication or test work performed or material used and as to the rate of progress of the work, and will decide all questions which may arise as to the interpretation of the specification and drawings.

Company's inspector has authority to stop the construction or fabrication or test work whenever, in his opinion, such stoppage may be necessary to ensure its proper execution.

COMPANY has authority to reject any of the Contractor's organization does not show the enough experience to follow the approved specifications or procedures or for any behavior may affect the COMPANY prestige or Syrian Arab Republic laws.

CONTRACTOR shall afford the Company's inspector every facility to inspect and observe preparations for performance and completion of the construction, fabrication and testing activities

Note:

Inspection shall not relieve CONTRACTOR from any duties, obligations, responsibilities or liabilities under this Contract.

      - CONTRACTOR  inspection

It is the CONTRACTOR responsibilities and obligation to provide all personnel, tools for all PROJECT disciplines inspection activities

The CONTRACTOR inspector is any of the individual(s) organization designated by the CONTRACTOR and accepted by the COMPANY’ to work for all matters relating to quality control, testing and acceptance of the work described in the scope of work.

At least the CONTRACTOR shall maintain full time of inspection at all disciplines and activities to ensure that all activities within the approved drawings, specification, standards and cods and meet all this RFQ requirements

The CONTRACTOR organization chart inspection team shall include but not limited to the following:

- Material inspectors

- Pipe line and piping inspectors

- Rotating machines inspectors

- welding inspectors

- NDT inspectors

- coating, painting and insulation inspectors

- hydro testing inspectors

- civil (building, foundation and steel structural) inspectors

- Instruments/ control inspectors.

- Electrical inspectors

- Cathodic protection inspectors.

- Telecom inspectors

      - Third Party Inspection.

The CONTRACTOR shall be responsible for the third-party inspection and test of equipment in the vendors/manufacturer shop in order to ensure conformance to the CONTRACT specifications.

The third-party inspection agency shall be proposed by the CONTRACTOR and accepted by COMPANY

The main equipments and material to be procured by the CONTRACTOR shall be procured with third party inspection acceptance

The CONTRACTOR shall advise the COMPANY six (6) weeks at least in advance for any shop-testing schedule of critical equipment in order for the COMPANY to assign their authorized representative to witness such test.

COMPANY approval shall not relieve CONTRACTOR from his obligations, responsibilities or liabilities under this CONTRACT to hand over the COMPANY safe and easy operable PROJECT within these RFQ specification, codes and standards

    - shall:	A mandatory requirement

    - should:   A strongly recommended requirement

    - could:	A possible course of action

    - Mechanical Completion Certificate (MCC)

COMPANY shall issue the Mechanical Completion Certificate (MCC) when the following activities have been performed:

- All construction works completed and accepted.

- Hydro test accepted.

- Inspection records complete and accepted by the inspector

- System cleaned and dried as per RFQ codes, standards and specifications.

- Instrument’s calibration sheet and loop check as per design.

- Commissioning and initial start up spare parts and consumable are on site.

- All documentation, drawings and manuals necessary for operation are on site.

- All categories (A) punch list item was released, fixed by CONTRACTOR and accepted by       COMPANY.

- All the red - marked up drawing (signed by COMPANY /CONTRACTOR   representatives) had been handed to the COMPANY and accepted.

    - Performance tests:

After finishing the commissioning activities and successful start up of all facilities and the PROJECT is proven to be capable to sustain the design flow conditions for uninterrupted operability test with period of 24 hours minimum

The CONTRACTOR shall perform with the presence of the COMPANY operation staff the performance tests of the PROJECT and perform successful execution of 72 continuous hour of operation according to these RFQ specifications and design condition and approved CONTRACTOR procedure

    - Provisional Acceptance Certificate (PAC)

COMPANY shall issue the Provisional Acceptance Certificate (PAC) when the following have been completely performed and accepted:

- Mechanical Completion Certificate (MCC) issued and signed by COMPANY.

- All pre-commissioning activities done by the CONTRACTOR and accepted by COMPANY according to the pre-commissioning requirements

- All commissioning activities and responsibilities done by the CONTRACTOR and accepted by COMPANY according to the commissioning requirements.

- Successful performance test accepted by the COMPANY according to the approved procedure

- All punch list item category (B) fixed by the CONTRACTOR and accepted by COMPANY.

- All the blue- marked up drawing (signed COMPANY /CONTRACTOR representatives) had been handed to the COMPANY and accepted.

The CONTRACTOR will be responsible for the new Facilities until the Certificate of Provisional Acceptance (PAC) has been signed and issued by COMPANY.

  - Scope

The Contractor's scope includes the Engineering, Procurement, Delivery and Complete Installation and construction of the facilities, with as minimum as described in these RFQ tender book and all associated drawings, specifications and documentation, and anything herein contained.

The omission of any essential provision here from, cannot be construed to relieve the CONTRACTOR from any duty or obligation, necessary for the complete installation of the facilities to be ready for use, safe and easy operation as a complete system in safe conditions.

The CONTRACTOR shall take full responsibility for all work associated with interfaces with existing COMPANY and Third-Party Facilities, such as electrical connections, pipeline and piping connections, cathodic protection, fiber optic telecommunications and control cable connections etc.

This shall include the site visits to the owners of the existing facilities in order to investigate exact location and type of existing facilities, obtaining of approvals, permits, permission for locating and methods of interfacing, ensuring compatibility between new work and existing facilities, installation of all systems/facilities to ensure a safe, operable interface and any remedial action necessary to return the existing facilities to its original condition.

The COMPANY should render assistance wherever possible and if required to accelerate the job within the contract’s terms, conditions and obligation without any time/cost impact to the COMPANY.

The CONTRACTOR shall keep the COMPANY fully aware of all interface discussions, activities and progress.

Interfaced parties shall also be kept fully informed of the planning and operations within those areas that affect them.

  - Engineering

The CONTRACTOR shall have the expertise in the design and preparation of equipment specifications, data sheets, calculations, requisitions, detailed pipeline alignment sheets, CADD drafting, computer process simulations and technical bid evaluation and all engineering requirements may be necessary to safe design and easy operable PROJECT

(For more details see section 2- Engineering Scope).

  - Procurement

All material and equipment/instruments supplied for the “ARAB GAS PIPELINE PROJECT PHASE II shall be suitable for the PROJECT conditions (environmental, site and gas composite) as defined in the “EXHIBIT-G, Data Reference and Contract’s General Specification”.

    - Purchasing

- The CONTRACTOR shall purchase or otherwise provide all materials, equipment, supplies required for the installation and timely completion of the PROJECT.

- Line pipe  , Valves , Actuator ,Line break ,Compressors ,DCS system , Telecom System ,Online Chromatograph ,Ultra Sonic Flow Meter ,Instruments and its accessories to be supplied by the CONTRACTOR shall be new /unused and purchased according to the company vendor list only

- Other Equipment, materials and Construction supplies shall be purchased from the first class and good known vendor/manufacturers included in the approved vendors/manufacturers List which will be issued prior to the contract signing in accordance with specifications and requirements of the contract.

- The COMPANY has the right to reject any materials or equipment supplied or intended to be supplied from any vendors/manufacturers are not in the approved list without any increase in the contract prices or change in the PROJECT time schedule.

- If the CONTRACTOR claims that a vendor/manufacturer listed in the Company's approved final list, cannot for any reason supply the materials and equipment required and wishes to add other vendors/manufacturers to the list, then CONTRACTOR shall submit to the COMPANY, a documented letter describe the deficiencies to provide the material  from the original vendor/manufacture written by the manufacturer /vender them self , together with the purchase requisition for the material and equipment and the name of the new vendor/manufacturer attached with references for the materials, equipment and supplies.

COMPANY shall review the new vendor references and comments.                 COMPANY shall have the right to reject any new Vendors without any cost/time impact to COMPANY.

- Any of Sub Contractors (if any) named by CONTRACTOR during signing the contract, shall not be changed without Company's approval and as per procedure specified above.

- The selection of vendors/manufacturers shall consider the technical and commercial criteria.

1.4.2 Expediting

The CONTRACTOR shall perform all the expediting required for all their material purchases and shall ensure that the vendors/manufacturers and or sub-CONTRACTOR(s) comply with the PROJECT specifications, and no delay will affect the COMPANY time schedule.

1.5 delivery and transportation

CONTRACTOR Delivery and Transportation shall include but not be limited to the following activities for CONTRACTOR furnished items including SPARES:

- All transportation from vendors/manufacturers shop to port, aircraft or alternative means of transport.

- All transport of materials/equipment from country of origin to the job sites in Syria (air, land or sea).

- All delivery, logistical and custom clearance functions in the country of origin as well as in Syria.

- All transport in Syria to the installation jobsites.

- All related insurance

- All loading, off loading and setting at job site.

- All preservation and storage, en-route and at site.

- All material will be accompanied by the relevant documentation, e.g. material certificate.

  - Construction

The CONTRACTOR shall have the expertise in the construction of facilities and installation of equipment to perform all construction works to complete the PROJECT as per contract specification and requirement

(For more details, see section 3-Construction scope).

1.7 CONTRACT SCHEDULE

The COMPANY milestone schedule as listed in “EXHIBIT-D, Contract Schedules” shall be complied and confirmed by CONTRACTOR.

CONTRACTOR shall provide a detailed and complete schedule indicating activity start and completion times. This schedule will conform to the milestone dates of Company's Schedule.

The schedule shall address for the project as a minimum the following:

- Basic/Detail design complete

- Purchase orders issue

- vendor selection

- Mobilisation

- Various Construction activities according to the COMPANY requirements and priorities

- Materials and Equipment arrival to the job site.

- DCS/Control system’s Configuration and Programming, Factory Acceptance Test (FAT), and Site Acceptance Test (SAT)

- Commissioning and hydrocarbon introducing

- Documentation and as built drawings delivery

  - Pre-Commissioning

The CONTRACTOR shall have the expertise in the pre-commissioning and all activities associated to the bringing the constructed facilities into such stat

as will permit introduction of process media and commissioning of the PROJECT as per contract specification and requirement

Pre-commissioning shall include, all activities associated with bringing the constructed PROJECT into such a state as will permit introduction of process media and commissioning of the facilities.

Pre-commissioning shall include but not limited to the following:

- Successful execution of hydrostatic, mechanical and electrical tests;

- All temporary facilities required for handling Hydro test and flushing fluids.

- Loop testing, calibration and function testing of control, monitoring and SCADA system, and telecommunication system.

- Checking of the alignment, rotation and tightness of all elements of the pipeline and facility(s);

- The provision of on-site vendors/manufacturer representative(s).

- Physical inspection of all items, plant, pipeline or equipment to guarantee conformance with PROJECT related drawings and Specifications.

- The flushing, cleaning and drying of the completed pipeline and facilities to permit operation without damaging or failing mechanical equipment or adulterating the product.

- Rotating equipment alignments are checked and prime movers are run for at least four (4) hours uncoupled.

- all instruments, control panels, electrical and mechanical equipment, including auxiliaries and  control systems, are serviced, adjusted, loop-tested,  calibrated and set for normal operation.

- All function tests identified by COMPANY.

CONTRACTOR shall be responsible for the performance of all pre-commissioning works, which shall be witnessed and signed off by COMPANY’s authorized representative(s).

CONTRACTOR shall compile a complete pre-commissioning manual, which shall incorporate all physical checks, tests and verifications (including equipment vendors/manufacturer recommendations)

CONTRACTOR shall issue the finalized pre-commissioning manual (as agreed between COMPANY and CONTRACTOR) no later than three weeks after completion of detailed design

CONTRACTOR shall carry out all pre-commissioning checks in the presence of COMPANY’s authorized representative(s) and shall ensure all checks are documented, witnessed and signed off by CONTRACTOR and COMPANY’s authorized representative(s).

Prior to commencement of commissioning activities CONTRACTOR shall formally hand over the completed pre-commissioning and inspection manuals to COMPANY's authorized representative(s), after site physical check with CONTRACTOR to ensure the preparedness of the pipeline for introduction of hydrocarbons

After COMPANY’s satisfaction that all pre-commissioning tests and verifications have been properly executed and registered, CONTRACTOR will be formally notified of COMPANY's intention to introduce hydrocarbons.

CONTRACTOR shall, promptly rectify any deficiencies identified by COMPANY, to COMPANY's satisfaction.

  - Commissioning

Commissioning shall be conducted by CONTRACTOR in accordance with the approved commissioning manual, after CONTRACTOR has demonstrated to COMPANY’s satisfaction that, all pre-commissioning activities have been successfully completed.

CONTRACTOR shall perform the complete commissioning actions, in strict accordance with the procedures stated.

CONTRACTOR remains responsible for the correct and safe operation of the facilities during commissioning.

All modifications required for safe operation shall be registed as blue marked up drawing to be considered on the final as built drawings

Commissioning shall be conducted by CONTRACTOR in accordance with the COMPANY approved commissioning manual, after CONTRACTOR has demonstrated to COMPANY’s satisfaction that, all pre-commissioning activities have been successfully completed.

During the initial start up and commissioning of the PROJECT or parts thereof, CONTRACTOR shall make available vendors/manufacturer representative(s) as defined in the COMPANY approved commissioning procedures or as otherwise identified and agreed as needed.

CONTRACTOR is required to attend daily commissioning meetings at which COMPANY’s authorized representative(s) will require detailed briefings from CONTRACTOR as to which systems will undergo commissioning.

CONTRACTOR is advised that all interfaces between Arab gas pipeline phase II 36” pipeline at AL Foreqls existing manifold or the interfacing with the gas co-ordination center and facilities shall be fully identified and discussed with COMPANY's authorized representative(s).

CONTRACTOR shall fully define the possible effects of his commissioning activities on the existing process, instrumentation and electrical systems.

These effects shall be documented by CONTRACTOR and be handed over to COMPANY's authorized representative(s) at each daily commissioning meeting.

Where in Company's opinion, commissioning activities are likely to cause upsets to the existing pipeline and facility(s), COMPANY reserves the right to witness CONTRACTOR's performance of such commissioning activities.

COMPANY reserves the right to conduct, unannounced audits of the commissioning work being performed by CONTRACTOR. should the activities of the CONTRACTOR not conform with the COMPANY approved commissioning procedures, agreed daily commissioning briefings or COMPANY safety regulations/practices, COMPANY shall instruct CONTRACTOR to cease commissioning activities until such time that the situation has been rectified to the satisfaction of COMPANY's authorized representative(s).

Commissioning by CONTRACTOR shall include but not limited to the following:

- Introduction of hydrocarbon into the newly constructed pipeline and facilities after successful leak testing.

- Successful testing of control and shutdown systems associated with the existing and newly constructed pipeline and facility(s);

- The successful operation of SDV and BVS valves, running of scraper, metering equipment, and rotating machines, associated with the constructed PROJECT.

- Performing of Site Acceptance Test (SAT) of control/monitoring system.

- Testing and, if appropriate, recalibration of control loops and instruments under normal operating conditions;

- Availability of on-site vendors/manufacturer representative(s);

- successful execution of uninterrupted 24 hour of operability tests for the PROJECT

- Successful execution of 72-hour acceptance tests in accordance with these RFQ specification and design conditions and CONTRACTOR’s procedures for acceptance and performance testing which is approved by COMPANY.

- the successful execution of performance and acceptance tests;

- the proper handover of the new facilities to COMPANY production operations department

- all shutdown and relief systems are tested for proper functioning at the set values during a complete system test;

- all instruments and control panels are tested for control/alarm function at the turn down with process media in the system;

Before starting the 24-hr test CONTRACTOR will have completed, as a minimum, the following:

- installation of all equipment

- perform the all tests required

- all test packs signed off

- All commissioning spares available at site.

Relevant documentation shall be presented to COMPANY representative(s) for review.

CONTRACTOR shall perform the complete commissioning actions, in strict accordance with the procedures stated.

CONTRACTOR remains responsible for the correct and safe operation of the facilities during commissioning.

  - documentation

Documentation shall be provided by CONTRACTOR as per requirement of schedule “PEA- PROJECT execution and Administration”, provided in EXHIBIT-F.

  - Warranty/Guarantee

CONTRACTOR shall warrant/guarantee the equipment and workmanship as per the requirement of EXHIBIT-K, Warranty of workmanship and Materials.

  - CONTRACTOR Services

    - Scope of Work

Spare parts, special tools and testing equipment, shall be procured and delivered by CONTRACTOR to COMPANY’s al Rayan yard (15 km east of Homs City) in accordance with the following provisions.

    - Spare Parts

- CONTRACTOR shall supply all spare parts, consumable and operating supplies:

- Necessary for Start-up, Commissioning and for Initial Operation until the issue of the Provisional Acceptance Certificate (PAC) of the Work; and

- Any other spare parts specified elsewhere in this RFQ.

The nature and quantities of such spare parts shall be as recommended by the vendors/manufacturer of the various equipment items.

Any remaining initial spare parts and materials as supplied by CONTRACTOR for the PROJECT shall be handed over to COMPANY upon issue of the provisional acceptance certificate "PAC", at no additional cost to COMPANY.

1.12.2.2 CONTRACTOR shall procure, supply, transport and deliver all spare parts, consumable and operating supplies:

- Provided in the EXHIBIT-J “CONTRACTOR Supplied Materials”.

- Necessary to ensure, two (2) years of normal continuous operation of the facilities to be constructed under this Contract as recommended, documented and approved by Manufacturers Of various types of devices, instruments and equipment.

All costs associated with procurement of all materials requested in above mentioned items 1.12.2.1&1.12.2.2 and also such as handling fees, transportation, etc. shall form part of the Contractor's lump sum pricing.

CONTRACTOR shall arrange for equipment suppliers to submit to him fully completed and separate SPIR forms for each category of spares as specified above, showing the recommended spares for each item of equipment.

Completed SPIR forms shall be forwarded to COMPANY's authorized representative(s) together with all vendors/manufacturer Data Books for approval prior to CONTRACTOR ordering spare parts consignments.

The submission to COMPANY's authorized representative(s) shall include the originals and copies of information received from vendors/manufacturers.

A guide to completion of the SPIR form is included in EXHIBIT-L, SPIR Form complete with Instructions” and should be forwarded to each vendors/manufacturer with the SPIR form.

No deviation from the vendors/manufacturer's recommended listing of spare parts shall be allowed without prior COMPANY approval.

Vendors /manufacturers recommended listing, to be supplied by CONTRACTOR to COMPANY, shall acknowledge the remote overseas location of the installation and the two-year spare part time frame requirement.

CONTRACTOR shall ensure there are full inventories of spare parts, as described in this Section, at the site 30 days prior to commissioning of the facilities or parts thereof.

The Provisional Acceptance Certificate (PAC) shall not hand over until two years recommended spar part and material included in EXHIBIT (J) Available at site

The spare parts, furnished by CONTRACTOR hereunder shall be manufactured using the same drawings, specifications, processes and tolerances and using identical materials as used in the original materials and equipment which the spare parts are intended to replace.

Such spare parts shall be fully interchangeable with the original materials and equipment or portions thereof without modifications to such spare parts or to the original materials or equipment.

Contractor's furnishing of spare parts pursuant to this article shall not relieve CONTRACTOR of its obligations under the “EXHIBIT-K, Warranty of Workmanship and Materials”.

    - Special Tools and Testing Equipment

CONTRACTOR shall supply, with and as part of the equipment, all special tools, testing equipment and calibration equipment etc... Which will become the property of the COMPANY.  These are of the type not normally used by craftsmen and which are required to test, calibrate, service and maintain the various items of equipment included in the work.

The nature and quantities of such special tools and testing equipment shall be as recommended and documented by the vendors/manufacturer of the various equipment items.

CONTRACTOR shall compile a list of all the special tools and testing equipment and shall submit it to COMPANY's authorized representative(s) for approval.

the submission to COMPANY's authorized representative(s) shall include copies of information received from vendors/manufacturer and shall show, as applicable, for each special tool and testing equipment, item, name, quantity, specification and operating instructions.

CONTRACTOR shall ensure there are a full inventory of special tools and testing equipment at the site 30 days prior to commissioning of the pipeline and facility(s) or parts thereof.

  - Contractor's On-Site Facilities and Services

CONTRACTOR shall furnish all items specified in the scope of works, all exhibits, appendices and documents provided in this RFQ.

In the implementation of the foregoing, CONTRACTOR shall comply with the provisions set forth below.

Unless provided otherwise, no separate payment shall be made to CONTRACTOR for furnishing such services; all CONTRACTORs’ costs pertaining thereto shall be deemed to be included in the contract price.

CONTRACTOR shall furnish all personnel, buildings, facilities, equipment and supplies and shall service and maintain such buildings, facilities and equipment so as to provide accommodation and catering for CONTRACTOR's entire workforce.

In fulfilling the requirements of this article CONTRACTOR may elect to construct and operate an on-site camp.

In this event, the location, layout, construction standards, facilities and operations of the camp shall be subject to the prior and/or ongoing review and approval of COMPANY's authorized representative(s).

    - First Aid

CONTRACTOR shall provide an on-site first aid capable to provide first aid services to CONTRACTOR's entire on-site workforce, including the on-site employees of all sub- CONTRACTOR's , vendors/manufacturers and company if any.

In the event any medical situation is beyond the capability of the on-site first aid service, then CONTRACTOR shall transfer the patient to a hospital or other medical facility as appropriate.

    - Security

CONTRACTOR shall furnish all personnel, equipment and supplies required providing a continuous on-site security service.

The purpose of such security service shall be to permit entry to the construction sites of only those persons authorized by COMPANY, to assist in the prevention of pilferage of material items, to maintain orderly conduct on the site and to attend to other schedule and unscheduled security situations.

CONTRACTOR shall follow the requirements of the laws of the SYRIAN ARAB REPUBLIC in the performance of such security services.

    - Sanitation

CONTRACTOR shall furnish all personnel, equipment and supplies to provide services and maintain adequate sanitary and decent on-site sanitation facilities.

Such facilities shall be provided adjacent to each location where work is being performed.

CONTRACTOR shall also perform daily clean up of the site so as to maintain a tidy and safe work environment which is vermin and vector free.

    - Project Signboards

On request of COMPANY, CONTRACTOR shall provide and erect a PROJECT signboard at each principal area at the site where work is performed.

The cost of these signboards shall be included in the Contract Price.

Such signboards shall show both in the Arabic and English language the PROJECT title, the Contract title and number and COMPANY's and CONTRACTOR’s names and logos.

Such signboards shall be subject to COMPANY's authorized representative(s)' approval with respect to size, construction, wording, calligraphy, support, location and numbers

Upon completion of the work, CONTRACTOR shall at its expense remove all such signboards and cleans up the applicable areas to the satisfaction of COMPANY's authorized representative(s).

    - Vendors/Manufacturer Representative(s)

CONTRACTOR shall provide on-site services of vendors/manufacturer representative(s).

Such vendors/manufacturer representative(s) shall be an employee(s) of or accredited to the vendors/manufacturer or vendors/manufacturer of the applicable material and equipment and he shall be knowledgeable in the technical aspects of the material and equipment.

Vendors /manufacturer representative(s) shall assist and advise CONTRACTOR and/or COMPANY (as the case may be) in the safe, proper and expeditious receipt, storage, handling, installation, testing, pre-commissioning, calibration and start-up of the applicable material and equipment and of the PROJECT as a whole.

Such vendors/manufacturer representatives shall be available on site at such times as are required on technical grounds and at such times as are necessary for CONTRACTOR to adhere to applicable contractual schedules.

In addition, such vendors/manufacturer representative(s) shall also be available on site at those times as COMPANY's authorized representative(s) may direct.

All CONTRACTORs’ costs incurred in the compliance with this article shall be deemed to be included in the Contract Price and such costs shall not be the subject of separate payment by COMPANY.

    - On-Site Offices and services for COMPANY’s staff

CONTRACTOR shall supply furnished office(s) as following:

- 6 (six) offices as minimum in each main camp.

Each office shall be furnished as minimum with the following :

-(1) One split  type (cold / hot) air conditioner .

-(2)Two wooden tables

-(4) Four wooden chairs

-(2)Two file cabinets

-(1) One latest version computer with all accessories (from the contract commencement date) and equipped with CD writers

- (5) Five latest version lap-top

- (1)One copy machine (A3/A4) for main

- (1)One fax machine

- (2)TWO telephone line.

- (5) Five laser jet printer

- (1)One color printer

- (2) Two furnished offices along pipeline rout .

In addition to daily offices requirement and daily janitorial services

- Daily accommodation and catering for15(fifteen) personnel for main camp

The company shall reject such furniture, accommodation and catering if did not meet the company satisfaction and acceptance

The cost of such services including telecommunication shall be deemed to be included in the Contract Price and such costs shall not be the subject of separate payment by COMPANY.

  - Company's staff training

The CONTRACTOR shall undertake providing training of:

- 20 (twenty) Personnel for a period of 2(two) weeks in the field at operating acknowledge of the various type of equipment and control system to enable Company's staff to operate of the facilities in safe conditions as per RFQ specification and standards

- Fifteen (15) Personnel for a period of three weeks, on operation and maintenance of Gas compressor unit and turbine at the site.

- 10 (ten) Personnel for a period of 2(two) weeks at operation and maintenance of the control and telecommunication systems at Vendors Manufacturer's workshops.

- 4 (four) Personnel for a period of 2(two) weeks at operation and maintenance of the Chromatograph at Vendors Manufacturer's workshops.

- Ten  (10) Personnel for a period of three weeks,  on operation and maintenance of Gas compressor unit and turbine at Vendor’s / Manufacturer’s Workshops

- 4 (four) Personnel for a period of 2(two) weeks at(operation, installation and maintenance) of sectionalizing valve ,line break and actuator for motorized valves

Fully accommodate and transportation outside Syria shall be at the contractor's account except air tickets, which shall be provided by COMPANY.

  - Drawings

CONTRACTOR shall provide all drawings for all activities of PROJECT.

CONTRACTOR shall keep a set of construction drawings which they will mark-up reflecting the As-Built Installations and shall submit such drawings red marked to the COMPANY within fifteen (15) calendar days of job completion as well as, As Built, drawings in both hard and soft copy to be delivered to COMPANY within one month from the date of issuing of Mechanical Completion Certificate (MCC).

By "As-Built", it means that the CONTRACTOR has adequately shown or provided additional sketches, to clearly convey the information for the actual pipeline, piping and instrumentation configuration etc.

Additionally, all as built drawings, configuration, programming and application software shall be provided on CD-ROM.

For detailing see section 2 engineering scope

  - discrepancies

In case a discrepancy arises or exists between codes, standards, drawings and documents, the most severe shall govern in the following priority:

RFQ tender documents.

(AFPC) scopes and specifications.

International Industry Codes and Standards.