9-pipeline SCOPE

  - General Description

    - Scope

    - Pipe line Design

    - Pipeline routing

    - Pipeline construction

  - Job Description

  - safety

  - material procurement

- general

- Line pipe Material

- pipeline fitting

  - Pipeline drawing.

- General

- Profile

- Maps and Drawings

      - Route Maps

      - Alignment Sheet

      - Property Plot Drawings

      - As-Built Drawings

- Pipeline hydro testing

- Testing

- Test Pressures Table

- drying

- discrepancy

9-Pipeline Scope

  - General Description

    - Scope

This Scope of Work covers the minimum requirements for the                                  ARAB GAS PIPE LINE PROJECT -PHASE II.

The CONTRACTOR’s scope of work shall includes, detailed pipeline route selection, detailed design, engineering, procurement, personnel, supervision, materials, consumables, construction, Hydro testing/drying, commissioning and start-up of:

Approximately 186 km of 36" NPS of API 5L X70 pipeline for the PROJECT, in accordance with all RFQ Specifications and Standards and Industry Codes and Standards

CONTRACTOR shall execute the installation of the pipeline between  Al Foreqls Area and the Aleppo PRMS  according to the COMPANY requirements

    - Pipe line Design

The CONTRACTOR shall supply detailed design for all disciplines required for the installation of pipeline.

The CONTRACTOR shall design the pipeline and his design shall include as minimum but not limited to the following:

- proposed Gas trunk line, gas line routing

- Pig launcher/receiver drawings

- Intermediate station drawings.

- P and ID's

- Plot plans (showing entry and tie-ins)

- cathodic protection systems schematics

- cathodic protection calculations

- Gas trunk line hold up calculations

- purchase orders for:

    - coated line pipe as described in Exhibit M

    - pipeline construction consumables like welding rods ,shrink sleeve coating, coating repair material, crossing sealing…etc

    - fiber optic cable

    - anchor ,isolation joints

    - piping ,fitting and valves for the block valve station ,pigging stations ,tie-in connection points…etc

    - sectionalizing valves

    - Launchers/receivers stations

    - Intermediate station.

In addition to:

    - Area classification drawings.

    - Design book

    - QC manual

    - The pipeline shall be designed in accordance with the relevant sections   of ANSI/ASME B31. 8, and as stated in this scope

    - The pipeline shall be designed taking into account the densities of WADI crossings.

    - The design shall take into account the operations, inspection and maintenance requirements, for safe and easy operating philosophy

    - CONTRACTOR shall take into consideration the external interference by third party is major cause of pipeline failures

    - All floodable sections of pipelines, high water table areas, river crossings, etc., should be stable under the combined action of hydrostatic and hydrodynamic forces.

    - The pipeline shall be completely suitable for the future intelligent pigging and geometrical inspection

The pipeline shall be suitable to pass pigs, inspection with intelligent pigs.

Permanent pigging facilities shall be justified based on an analysis of pigging frequency and operational constraints.

Pig launcher /receiver station shall be designed to do the same                          function (The launcher may be used as receiver according to operation              philosophy and vise versa)

    - The CONTRACTOR design shall put into account that the pipeline block valves shall be designed and located by the good engineering practice to achieve complete leak tight isolation

This block valve shall be equipped with easy and safe greasing system Equipped with valves for more safety precautions

In no case a check valve may be used instead of a block valve.

    - The spacing of sectionalizing block valves shall be determined to minimize risk to personnel, loss of product, and exposure to environment.

The appropriate method for this block valve actuation shall be determined from a study of the likely effects of a leak and acceptable released volumes, based on the total time in which a leak can be detected, located and isolated.

All sectionalizing block valves shall be remotely and manually operated.

    - The block valve station shall be equipped with leak detection.

    - The CONTRACTOR shall take in his design the ability and capability for operational and emergency pipeline depressurization at each end of the pipeline and at each sectionalizing valve location.

The capacity of the venting system should be such that the pressure in the pipeline can be reduced as rapidly as practicable.

    - The pipeline system SHALL be designed such that surge pressures cannot exceed MAIP at any point along the pipeline, and will not trigger the system for overpressure protection from the upstream facility if fitted.

Methods of preventing the generation of unacceptably high surge pressures including valve closure speed reduction or special fast-response pressure relief systems close to the point of surge initiation.

If not sufficient, strict adherence to well formulated operating procedures should be implemented.

    - The pipeline system, including equipment, design and installation shall conform to all applicable RFQ specifications and standards, International Codes and Standards including but not limited to that     specified in the “EXHIBIT-G, Data References and Contract’s General Specifications”.

    - Pipeline routing

    - Specific precautions against this type of hazard shall be addressed; this is particularly this pipeline transporting category D fluids.

    - The selection of the route shall take full account of the associated risks, particularly safety and environmental risks, the accessibility for maintenance and inspection.

The preliminary pipeline route has been selected according to the  following criteria:

- close to expected areas of demand

- avoids population areas and private land (as far as reasonably practical)

- maximizes use of public owned areas

- avoids terrain which difficult for pipeline construction

- facilitates easy access for construction.

- Minimizes adverse environmental impact.

    - Detailed survey data should be available prior to finalizing the pipeline route and carrying out detailed design. these data include:

- Population and building densities for the establishment of location classes, location of inhabited buildings, taking into account any future land development plans to accurately choosing the factor design for each wall thickness to be specified along the pipeline rout.

The factor design shall be according to this table

| fluid category | D |  |  |  |
| --- | --- | --- | --- | --- |
| applicable code | B31.8 |  |  |  |
| location classes | 1 | 2 | 3 | 4 |
| pipelines | 0.72 | 0.60 | 0.50 | 0.40 |
| Crossings |  |  |  |  |
| Private roads | 0.72 | 0.60 | 0.50 | 0.40 |
| Unimproved public roads | 0.60 | 0.60 | 0.50 | 0.40 |
| Roads, highways, streets and railways | 0.60 | 0.60 | 0.50 | 0.40 |
| Rivers, dunes and beaches | 0.60 | 0.60 | 0.50 | 0.40 |
| Parallel encroachments |  |  |  |  |
| Private roads | 0.72 | 0.60 | 0.50 | 0.40 |
| Unimproved public roads | 0.60 | 0.60 | 0.50 | 0.40 |
| Roads, highways, streets and railways | 0.60 | 0.60 | 0.50 | 0.40 |
| Fabricated assemblies | 0.60 | 0.60 | 0.50 | 0.40 |
| pipelines on bridges | 0.60 | 0.60 | 0.50 | 0.40 |
| Near concentration of people | 0.50 | 0.50 | 0.50 | 0.40 |
| pipelines, within plant fences, block valve stations and pig trap stations | 0.60 | 0.60 | 0.50 | 0.5 |

- Topographical data, location of rivers, roads and railways, including type and density of traffic.

- Records of any existing special features which will need reinstatement after construction is completed.

- Soil resistivity for cathodic protection design.

- Environmental data (climatic, floods, earthquakes, landslides, currents at river Crossings, vegetation, fauna).

    - pipeline construction

The construction activities include but not limited to the following:

- Pipeline survey.

- Soil investigations.

- The right of way clearing and grading.

- The trenches excavation and preparation.

- Area classification and line pipe stringing.

- All crossing with (roads, railway, swamps, wadis, rivers, power and telecom cables, power cables, potable water system, sewerages and other pipelines etc….)

- Pipeline bending, welding, NDE examination, coating, lowering, fiber optic cable laying and backfilling.

- Cathodic protection system installation.

- Telecommunication system installation.

- Pipeline cleaning, sizing, hydro testing, drying and purging.

- Right of way cleaning up and marking

- Demobilization.

- As built drawings

The CONTRACTOR shall provide all necessary calculations and procedures to ensure that the pipeline is installed in a safe and timely manner and with minimum impact on the environment.

The procedures should include as a minimum:

- Safety and Environment

- Quality assurance

- Right of way

- trenching

- Stringing

- cold bending

- Welding (pipeline, tie-in, golden and repair)

- non-destructive testing

- Field joint coating and repair coating

- Lowering-in

- backfilling

- site reinstatement

- Roads, railways and river crossings

- WADI crossing

- Concrete coatings for river crossings

- Permanent markers and barriers

- Fabricated assemblies

- Cathodic protection

- Filling, cleaning and hydrostatic testing

- Pre-commissioning

- Preparation of as-built records

The key equipment used by the CONTRACTOR should be fully tested on mobilization to prove that the requirements of the work can be met.

Care shall be taken during construction that debris, muddy water etc., do not enter the pipeline.

Golden welds shall be prepared and executed in accordance with AFPC Specification ECD-24 ‘Golden Weld Guidelines’.

  - job description

The CONTRACTOR PIPE LINE scope shall cover all the aspects included but not limited to these requested and described in the PROJECT which described in EXHIBIT B (scope of work)/section 1 general scope and definitions.

The CONTRACTOR shall be fully aware about the following:

- It is the CONTRACTOR’s responsibility to gather all information along the pipeline route including obstructions during the bid period.

- As-Built drawings shall be completed in one system.

- CONTRACTOR shall be responsible for completing the As-Built details for all the Tables on the Typical Drawings.

- Pipeline radiography shall be 100%.

- The COMPANY shall not procure any materials

- CONTRACTOR shall provide personnel, supervision, construction equipment welding rods, shrink sleeves, consumables, concrete, radiographic materials, repair kit sand all hydro testing, cleaning, drying etc. for the complete safe operable PROJECT.

- CONTRACTOR shall provide a Typical River, WADI /Canal, and Major and Minor Road Crossing.

- The remaining quantities of the (pipeline which are not used) shall be transported and returned back and handed over to the COMPANY’s Rayan Warehouse.

  - safety

The CONTRACTOR shall work to the highest achievable safety and environmental standards during all the pipeline construction stages.

The safety performance of all staff involved in the work shall be monitored and recorded. Regular safety inspection of the construction sites shall be carried out, to ensure compliance with the relevant procedures, as well as maintaining awareness of all staff regarding potential hazards. Refer to EXHIBIT F /HSE

  - material procurement

- general

The CONTRACTOR shall provide all materials, line pipe, labor, tools and construction equipment for the pipeline installation and facilities in accordance with Drawings, General Specifications, Codes and Standards and all aspects stated in this tender exhibit and annexes and correspondences.

The CONTRACTOR shall identify critical items of equipment and other materials and shall make appropriate arrangements to order and have such items delivered to meet the required overall completion date.

- Line pipe Material

Detailed line pipe specifications are described in EXHIBIT- M

- pipeline fitting

All fittings to be installed in the pipeline shall be procured using the MESC system, as per AFPC Specification Schedule Q ‘Pipe, Valves, and Fittings’ with particularly attention to the EXHIBIT B –section 5 mechanical scope

This fitting shall be compatible with the line pipe material in terms of weld ability and also conform to the bevel geometry constraints detailed in the pipeline codes.

  - Pipeline drawing.

- General

The CONTRACTOR shall supply all Drawings, alignment sheets, specification lists and all other documentation required completing the PROJECT.

The CONTRACTOR shall provide all the Drawings and is responsible to show the all details of the work and to ensure the Drawings are correct and complete before beginning the work

This drawing shall be based on the accurate field survey

CONTRACTOR shall be responsible for all survey work prior, during and upon completion of construction work as well as Built work.

CONTRACTOR shall perform the survey work specified hereunder using proven equipment and techniques.

COMPANY shall review pre-construction route maps and pipeline centerline alignment sheets before any pipeline construction works begins

The field survey shall be tied-up to national geodetic grid and nationally established geodetic points.

All significant topography and physical structures which might affect pipeline construction and/or maintenance shall be located and included on the Route Maps and Alignment Sheets.

All significant topography and physical structures which might affect pipeline construction and/or maintenance shall be located and included on the Route Maps and Alignment Sheets. These features include, but are not limited to, streams, washes, roads, trails, WADI's, bridges, culverts, buildings, pipelines, power lines, buried cables, fences, cultivated areas, swamps or wet areas, rock outcrops, railways, archeological sites, vegetation and soil characteristics, quarries, or any other natural or cultural features.

CONTRACTOR shall make every attempt to identify underground pipelines, cables, etc.

During the centerline survey, CONTRACTOR shall sweep the full centerline route of the pipeline with a "pipeline/cable detector".

When an underground structure is encountered, it shall be staked and identified with a description, size, depth and owner if at all possible.

Existing cables, pipelines, tunnels, etc., if indicated on the Drawings are for information only.

COMPANY does not guarantee that the information shown on the Drawings is either complete or correct.

CONTRACTOR is entirely responsible for detecting and locating all underground obstacles whether shown on the Drawings or not.

- Profile

The CONTRACTOR shall establish the profile of the survey centerline.

Elevations shall be obtained at all sharp breaks in slope, at high and low points, and at least every 100 meters on gently sloping terrain. Sufficient data on top and sub soil shall be obtained on active farm land, marsh land, road, railroad, wash, WADI and river crossing profiles for permits applications and design criteria.

- Maps and Drawings

- Route Maps

CONTRACTOR shall draft the survey on a Route Map covering the pipeline Route, centerline alignment, ROW, POS as well as all pertinent physical and topographical features.

The map shall also include land ownership within the ROW with ties to corners and topographic features.

The map scale shall not be smaller than 1/10,000 in length or 1/1000 in width.

The map shall also show the contour line at 1 m.

Elevation spacing and at a closer spacing on critical areas.

- Alignment Sheet

CONTRACTOR shall prepare pipeline Alignment Sheets showing the plan and profile of the pipeline centerline.

The Alignment Sheets shall clearly present all pertinent information including horizontal distances (partial and cumulative); horizontal angles; grade, bottom of ditch and centerline elevations; pipeline indicator markers, CP markers, crossings and all other information as required elsewhere in this Specification.

The horizontal scale shall not be smaller than 1/1000 and the vertical not smaller than 1/200

CONTRACTOR shall address all his field survey of the pipeline route on the alignment sheets drawing which includes but not limited to the following:

- Contour lines of the pipeline Route.

- Physical features that may affect the selection of pipeline centerline alignment and construction.

- Pipeline centerline alignment.

- Sloped-distance of alignment to provide the actual pipeline length.

- Horizontal distance of alignment for ROW acquisition.

- Property plots

- Identification of all roads, railways, WADI’s, cables, pipelines, ground beds etc. which cross the proposed pipeline route.

- All features included in 200m width of the pipeline centerline but are not limited to, streams, washes, roads, trails, WADI's, bridges, culverts, buildings, pipelines, power lines, buried cables, fences, cultivated areas, swamps or wet areas, rock outcrops, railways, archeological sites, vegetation and soil characteristics, quarries, or any other natural or cultural features.

- The alignment drawing shall show as minimum:

- The pipeline center line with all surveyed features around.

- The horizontal distance.

- The cumulative progress distance.

- The human occupancy building in 200m width of each side of pipeline center line.

- All pipeline crossing.

- Pipeline specification.

- Pipeline wall thickness.

- Pipeline coating specification and thickness.

- Pipeline chainage marking with all other pipeline markers.

- Pipeline elevation.

- Pipeline trench minimum cover requirement.

- Pipeline horizontal bends degrees.

- Cathodice protection points and test station.

- Soil charactricities.

- Geotechnical bearing location and data.

- Pipeline casing carrier.

- Pipe line concrete coating.

- Pipe line concrete slab

- Property Plot Drawings

CONTRACTOR shall prepare a Plot Drawing for each property location and for every property parcel crossed by the proposed ROW.

Plots shall locate surveyed alignment with respect to title information. Legal descriptions shall be furnished with each plot. Each plot shall be certified correct by the CONTRACTOR.

Scale of plot shall be approved by COMPANY.

- As-Built Drawings

A comprehensive set of as-built documents, to be included in the hand-over documentation, shall be produced during construction and retained for the life of the pipeline. These should include, as a minimum:

- Changes to original design, with reasons.

- Pipe tally giving the size, grade, wall thickness, identification number, coating details, and location of each pipe joint used during construction.

- Specifications used for field jointing (welding and coating).

- Non-conformance reports and remedial actions taken.

- Radiographs of the welds (radiographs need be retained for a period of five years only).

- Detailed survey of the as-laid position of the pipeline, including burial depth as applicable.

- Pigging records.

- Hydro test certificates.

The design drawings shall be updated based on the as-built condition, before hand-over of the pipeline to the operations function.

- Pipeline hydro testing

    - Testing

The CONTRACTOR shall supply the necessary equipment and personnel required for cleaning, hydrostatic testing, drying and purging.

Hydrostatic testing shall be done in the presence of the COMPANY’s representative in accordance with “Schedule PL-CP, Construction Practices for pipelines”.

The CONTRACTOR shall prepare a detailed test procedure and shall submit it to the COMPANY for approval one-month prior of work starting.

    - Test Pressures Table

| NPS Inches | Design Pressure BAR(g) | Min. Field Test Pressure BAR(g) | Max. Field Test Pressure BAR(g) |
| --- | --- | --- | --- |
| 36 | 75 | 93.75 | 98 |

    - drying

The drying temperature shall be at least minus 15 (fifteen) Celsius degree

- discrepancy

In case any discrepancies arise between the drawing the following priorities shall be applied

    - This specification

    - AFPC Specification PL-CP ‘Construction Practices for pipelines’

    - The relevant sections of the ANSI/ASME Codes, supplemented by this chapter, and any additional criteria resulting from the design.