.	دفتر شروط  حقوقي و مالي للملف رقم         / 2025

تنفيذ مشروع خط الغاز العربي المرحلة الثانية

Financial and Legal Tender Book Related to T/File No.       /2025

For ARAB GAS PIPELINE, PHASE II

| استنادا للقانون 51 عام 2004 المتضمن نظام العقود ولاسيما الفصل الرابع منه (طلب العروض). المادة الأولى: أولاً - وثائق العقد: يعتبر كل مما يلي جزء لا يتجزأ من شروطنا العامة والخاصة: 1ـ نظام العقود الصادر بالقانون رقم /51/ لعام 2004 2- دفتر الشروط العامة الصادر بالمرسوم رقم / 450/ لعام 2004 3- دفتر الشروط الخاصة الفنية والمالية والحقوقية. 4- العقد النموذجي الصادر عن رئاسة مجلس الوزراء المرفق بإضبارة الملف. 5- الإعلان الخاص بالملف رقم / 2025 ثانياً- تعريف المشروع: ويعني التصاميم والتوريدات والتركيب والأعمال المبينة في دفتر الشروط الفنية (مفتاح باليد) لخط الغاز العربي المرحلة الثانية الذي يمتد من محطة الصمام المقطعي 6011 على خط الغاز العربي المرحلة الأولى في منطقة الفرقلس شرقي حمص ب/50/ كم وحتى محطة تخفيض الضغوط والقياس في حلب (R-7003) والممتد من حلب بطول حوالي (186) كم. المادة الثانية: أحكام خاصة: - تقديم تأمينات أولية: بقيمة (5000000) دولار أمريكي فقط خمسة مليون دولار أمريكي ب ـ مدة التنفيذ للمشروع ( مفتاح باليد) : يلتزم المتعهد أن يسلم كامل المشروع خلال/22/ اثنان وعشرون شهراً من نفاذ العقد، وفق ما ورد بهذا العقد و ملاحقه الفنية (برنامج العقد) الملحق رقم /D /. ج- تبدأ المباشرة بالعقد خلال /7/ سبعة أيام اعتبارا من تاريخ تبليغ المتعهد لفتح الاعتماد ا لمستندي المعزز من قبل الإدارة وفق شروط العقد. د - تقديم تأمينات نهائية: تقدم التأمينات النهائية بنسبة 10 % من قيمة الإحالة خلال /15/ يوم من تبليغ الإرساء . ﻫ - آخر موعد لتقديم العروض: نهاية الدوام الرسمي ليوم / /2025. وتجزئة الطلبية: غير قابلة للتجزئة. ي- مكان تقديم العروض: تقدم العروض وتسجل لدى الديوان العام للشركة السورية للغاز بحمص –– ص.ب./4499 / - هاتف / 2496108—2496101 --12-00963 / فاكس / 2496640-12-00963 / المادة الثالثة: تقدم العروض ضمن ثلاثة مغلفات مختومة ومرقمة وتوضع هذه المغلفات في مغلف رابع معنون باسم الشركة السورية للغاز مديرية العقود والمشتريات ويدون عليه: 1ـ رقم الملف . 2ـ موضوع الملف. 3ـ موعد الإغلاق . 4ـ اسم الشركة العارضة وجنسيتها. 1) المغلف الأول ويحوي : 1ـ1الوثائق التي تثبت أن الشركة العارضة من الشركات المتخصصة بإجراء مثل هذه الأعمال والمحددة في دفتر الشروط الفنية وفقاً للملحق A الفقرة /2/ تعليمات للعارض البند /2-10/ تقديم العرض. 1-2 التزام العارض الأجنبي بتسمية وكيل تجاري في الجمهورية العربية السورية مسجلة وكالته لدى الجهات المختصة وفق أحكام المرسوم التشريعي رقم 151 لعام 1952 وتعديلاته ضمن الشروط والأحكام الواردة فيه وأحكام المرسوم 15 لعام 2001 . 1ـ3 تصريح من العارض بأنه اطلع على دفاتر الشروط العامة و الخاصة ( الحقوقية و الفنية والمالية ) و جداول بنود التوريدات و الأشغال المطلوبة الخاصة بالملف و أنه يلتزم بجميع ما ورد بهذه المستندات من شروط و أحكام . 1ـ4 الموطن المختار : أ- على العارض تحديد موطن مختار له في الجمهورية العربية السورية وعنوانه المفصل. ب- يمكن للعارض من رعايا الدول العربية غير المقيم في سوريا و العارض الأجنبي تعيين موطن مختار له خارج سوريا. ويعتبر هذا الموطن المختار ملزماً للمتعهد ولو انتقل إلى غيره ما لم يبلغ الإدارة خطيا عن موطنه المختار الجديد في البلد نفسها وإلا تعتبر كافة التبليغات المرسلة إلى المتعهد في الموطن المختار المحدد أولا" صحيحة. 1ـ5 الالتزام بأن المواد و ملحقاتها التي ستورد و تركب في المشروع موضوع العقد جديدة وغير مجددة . 1ـ6 تصريح يقدم من العارض يوضح فيه أنه لا يملك أي مصنع أو مؤسسة أو مكتب فرعي في إسرائيل و ألا يكون مشتركاً في أي مؤسسة أو هيئة فيها و ألا يكون طرفاً في أي عقد للصنع أو للتجميع أو الترخيص أو المساعدة الفنية مع أي مؤسسة أو هيئة أو شخص في إسرائيل و ألا يزاول مثل هذا النشاط في إسرائيل سواء بشخصه أم عن طريق وسيط و ألا يساهم بشكل من الأشكال في دعم إسرائيل أو مجهودها الحربي. 1-7 إشعار بدفع قيمة التأمينات الأولية وفق المادة / 7 / الفقرة / 12 / . - ألا يكون محروما من الدخول في المناقصات أو التعاقد مع الجهات العامة أو محجوزاً على أمواله حجزاً احتياطياً لصالح الجهات العامة أو حجزاً تنفيذياً.‏‏‏‏ - المغلف الثاني ويحوي: العرض الفني للأعمال المطلوبة منظما وفق دفتر الشروط. ولا يجوز أن يتضمن أي أسعار أو تحفظات آو شروط حقوقية آو مالية ولا يعتد بأي منها في حال ورودها. 3) المغلف الثالث ويحوي : العرض المالي مع جدول الأسعار الإفرادية والإجمالية للأعمال و المعدات و المواد و القطع التبديلية المطلوبة بدفتر الشروط الفنية( مفتاح باليد). الذي يجب أن ينظم من قبل العارض بصورة واضحة جلية دون حك أو شطب أو حشو ولا يجوز أن يتضمن أي تحفظات أو شروط حقوقية أو فنية ولا يعتد بأي منها في حال ورودها.‏‏‏‏ على أن تكون الأسعار موزعة وفق جدول توزيع الأسعار الموضح بالملحق A الصفحة /4 من 25 / في دفتر الشروط الفنية. المادة الرابعة : يقدم العارض تعهد مع العرض الفني بأن القطع التبديلية التي ستورد لصالح المشروع أصلية و مكفولة وفق النظم والمعايير الفنية المعمول بها من قبل الشركات الصانعة للمواد. المادة الخامسة: يرفض العرض في الحالات التالية: 1- عدم التزام العارض بشكل كامل بدفتر الشروط الحقوقي و المالي ومسودة العقد. 2- تسجيل العرض بديوان الشركة بعد موعد الإغلاق 3- صدور التأمينات الأولية بعد موعد الإغلاق . 4- تقديمه بصورة مخالفة لأحكام نظام العقود الصادر بالقانون رقم /51/ لعام 2004 . المادة السادسة: الضرائب والرسوم : 1- يتحمل المتعهد الضرائب والرسوم والنفقات التالية : 1-1 طابع العقد بنسبة /0,008/ (ثمانية بالألف) من القيمة الإجمالية للتعاقد يضاف إليها الطابع المالي بقيمة دولار واحد أو ما يعادله من العملة المعروضة؛ على أن يتم دفعها خلال مدة عشرة أيام من تاريخ تبليغ الاعتماد المستندي إلى المستفيد لأول مرة من قبل المصرف المراسل . 1-2 نفقات الإعلان وهي بحدود /600 / دولار أمريكي أو ما يعادلها بعملة العرض تحسم من قيمة الاعتماد . 1-3 الرسوم المترتبة على تصديق الوثائق من السفارات أو البعثات السورية خارج أراضي الجمهورية العربية السورية . 1-4 كافة الضرائب والرسوم المفروضة خارج أراضي الجمهورية العربية السورية. 1-5 نفقات تعديل الاعتماد المستندي و/ أو إجازة الاستيراد وإعادة التصدير , فيما إذا كان هو المسبب لذلك . 1-6 نفقات إصدار وتمديد الكفالات الأولية والنهائية . 1-7 كافة نفقات التخليص الجمركي باستثناء الرسم الجمركي. 1-8 نفقات شهادة المراقبة و التفتيش صادرة عن شركة مراقبة عالمية محايدة على أن تختارها الإدارة من ضمن قائمة أو قوائم يرشحها المتعهد . 2- تتحمل الشركة السورية للغاز النفقات التالية: 2-1 كافة الضرائب والرسوم المفروضة داخل أراضي الجمهورية العربية السورية المترتبة لقاء تنفيذ هذا العقد والتي لا تدخل ضمن الفقرة / 1 / من المادة / 6 / . 2-2 الرسم الجمركي فقط ضمن أراضي الجمهورية العربية السورية . 2-3 نفقات فتح وتعزيز الاعتماد المستندي طبقاً لشروط العقــد ونفقات تعديل الاعتماد المستندي في حال كانت الإدارة هي المسبب . 2-4 النفقات الناجمة عن الأضرار الزراعية واستملاك الأراضي ضمن حرم الخط المحدد بدفتر الشروط الفني فقط . المادة السابعة : أحكام عامة : 1- لا يقبل من العارض إلا عرض واحد ويعتبر العرض السابق في تسجيله بديوان الشركة هو المعتمد . 2- يعتبر كل عرض ساري المفعول مدة مائة وثمانون 180 يوما بعد موعد الإغلاق .وبعد انتهاء المدة يعتبر العرض مجددا حكما لمدة 180 مائة وثمانون يوما أخرى , ما لم يتقدم العارض بطلب خطي يسحب عرضه خلال السبعة أيام الأولى من مضي الـ 180 يوما . ولدى إرساء الطلبية على العارض الفائز تعتبرصلاحية العرض و التأمينات الأولية ممدة حكماً لمدة ستة أشهر اعتباراً من تاريخ تبليغه رسالة الإرساء. بعد انقضاء ستة أشهر فإن للعارض الفائز الحق خلال سبعة أيام من تاريخ انقضاء هذه المدة أن يسحب عرضه ، و إلاّ تمدد صلاحيته تلقائيا" لمدة ستة أشهر أخرى و هكذا. 3- القوة القاهرة: في حال حدوث القوة القاهرة, تطبق القوانين والأنظمة السورية, شريطة إعلام الشركة السورية للغاز بحدوث القوة القاهرة بكتاب خطي أو بالفاكس خلال خمسة عشر يوما من تاريخ حدوث القوة القاهرة , على أن يؤكد المتعهد ذلك بوثيقة رسمية مصدقة من غرفة التجارة والسفارة السورية في البلد الذي حدثت فيه القوة القاهرة أو من السلطات السورية المختصة في حال حدوث القوة القاهرة ضمن الأراضي السورية تحت طائلة سقوط حقه بطلب التمديد لمدة التسليم والاعتراض على غرامة التأخير. 4-غرامات التأخير: تحسب غرامة التأخير واحد بالألف من القيمة الإجمالية للعقد عن كل يوم تأخير في تنفيذ العقد على أن لا تتجاوز عشرين بالمائة من القيمة الإجمالية للإحالة. ويمكن أن تحسب غرامات التأخير على أساس الجزء المتأخر في تنفيذه شريطة تحقيق الشرطين المتلازمين التاليين : أ – يتم تسليم الأعمال المنجزة الأخرى من العقد ضمن المواعيد المحددة أصلا" . ب – أن يكون الجزء المتأخر إنجازه مستقلا في الاستعمال العادي عن الأعمال المنجزة ولا يؤثر على تشغيل المشروع. 5- السلفة و طريقـة الدفـع : يتم الدفع على الشكل التالي : 5-1 -السلفة: 10%(عشرة بالمائة) من قيمة جزء العملة الأجنبية ستدفع على شكل سلفة بالعملة الأجنبية, أي: - مبلغ دولار أمريكي - ومبلغ /100000000/ ل.س فقط مئة مليون ليرة سوريا لا غير سيدفع على شكل سلفة بالعملة المحلية. مقابل كفالة مصرفية يقدمها المتعهد للإدارة تعادل قيمة السلفة . هذه الكفالة المصرفية يجب أن تصدر أو تعزز من قبل المصرف التجاري السوري بحمص فرع رقم /1/ وفق النموذج المعتمد لدى المصرف وعلى أن يتم دفع السلفة بعد إعطاء أمر المباشرة. 5-2- طريقة الدفع: - جزء العملة الأجنبية مقابل المعدات و المواد و الخدمات و كذلك مقابل أجور النقل و التركيب و براءات الاختراع و رسوم التأمين و تكاليف التصاميم و النقل .......الخ كلها سوف تدفع على الشكل التالي : 5-2-1 خمسة وستون بالمائة ( 80 %) من قيمة جزء العملة الأجنبية يتم دفعها إلى المتعهد مقابل وثائق شحن المعدات و المواد على أساس سيف موقع العمل و التي سيقدمها المتعهد و المبينة في الفقرة 10-4-1 (من نموذج العقد المرفق) بموجب مصرف أجنبي من الدرجة الأولى عن طريق المصرف التجاري السوري فرع رقم (1) في حمص لصالح المتعهد و يتم إبلاغ المتعهد بالاعتماد المستندي هذا عن طريق المصرف المراسل . 5-2-2 أربعة بالمائة ( 5 %) من قيمة جزء العملة الأجنبية يتم دفعها إلى المتعهد مقابل وثائق الخدمات خارج الجمهورية العربية السورية و التي سيقدمها المتعهد و المبينة في الفقرة 10-4-2 من نموذج العقد المرفق و ذلك بواسطة اعتماد مستندي غير قابل للرجوع و قابل للتجزئة و معزز يفتح بالعملة الأجنبية لدى مصرف أجنبي من الدرجة الأولى عن طريق المصرف التجاري السوري فرع رقم (1) و لصالح المتعهد و يبلغ هذا الاعتماد إلى المتعهد بواسطة المصرف المراسل. 5-2-3 واحد و ثلاثون بالمائة ( 15 %) من قيمة جزء العملة الأجنبية يتم دفعها إلى المتعهد على شكل دفعات شهرية مقابل تقدم أعمال التركيب و الإنشاءات الهندسية و المدنية و النفقات الأخرى في سورية و ذلك بواسطة اعتماد مستندي غير قابل للرجوع و قابل للتجزئة و معزز يفتح بالعملة الأجنبية لدى مصرف أجنبي من الدرجة الأولى عن طريق المصرف التجاري السوري و لصالح المتعهد و يبلغ هذا الاعتماد إلى المتعهد بواسطة المصرف المراسل. 5-2-4 – جزء العملة المحلية : مبلغ / 1000000000 /ل.س (واحد مليار) ليرة سورية فقط لا غير. يتم دفعها كدفعات شهرية إلى المتعهد لقاء تقديم كشوفات شهرية لتقدم العمل المعتمدة من ممثل الشركة في الموقع و من الإدارة وذلك بواسطة حوالة مصرفية أو شيك مباشرة إلى حساب المتعهد في سورية. يقدم العارض عرضه المالي فقط بالدولار الأمريكي أو بالعملة الأجنبية القابلة للتحويل، وسيتم إضافة مبلغ العملة المحلية إلى القيمة الإجمالية للعرض المالي للعارض. 5-3 ينظم المتعهد جميع فواتيره الخاصة بكل مكونات قيمة العقد و ذلك على أساس القيمة الكاملة للفاتورة (أي 100% مائة بالمائة من قيمة الفاتورة) كما يجب أن يبين بوضوح في هذه الفاتورة قيمة الحسميات التالية. آ- سيتم حسم 10% عشرة بالمائة من القيمة الإجمالية لكل فاتورة لقاء تسديد السلفة المدفوعة بموجب المادة 9مكرر من العقد،. ب- حسم خمسة بالمائة (5 % ) من قيمة كل فاتورة كتوقيفات تدفع لقاء إصدار شهادات الإنجاز الميكانيكي من قبل الإدارة و بموجب تحويل برقي مصرفي لحساب المتعهد و ذلك خلال (40) أربعون يوما من تاريخ إصدار شهادة الإنجاز الميكانيكي ج - حسم خمسة بالمائة (5 % ) من قيمة كل فاتورة كتوقيفات تدفع لقاء إصدار شهادة الاستلام الاولي من قبل الإدارة و بموجب تحويل برقي مصرفي لحساب المتعهد و ذلك خلال (40) أربعون يوما من تاريخ إصدار شهادة الاستلام الأولي د- حسم عمولة الوكيل وفق النسب المحددة بصك وكالته من الفواتير مباشرة و هذا يعني أنه يجب أن يوضح في الفاتورة قيمتها الكاملة و كذلك المبلغ المستحق دفعه المتبقي من تلك القيمة بعد اقتطاع الحسميات المشار إليها أعلاه. 6- يجب أن يتضمن العقد النص التالي : يحق للملتزم التحلل من العقد دون أن يكون له الحق بالمطالبة بالتعويض عن أي عطل أو ضرر إذا لم تقم الإدارة بفتح الاعتماد المستندي بعد مضي ستة أشهر من إبلاغه المصادقة على العقد واعتباره نافذاً . وإذا لم يطلب التحلل من العقد خلال أسبوع من مضي الأشهر الستة ,تجدد التزامه حكماً ستة أشهر أخرى وهكذا . 7- فسخ العقد و سحب التنفيذ وفق أحكام المواد /54- 55- -59 -60 / من القانون رقم /51/ لعام 2004. 8- إن الأسعار التي تقدم من العارضين يجب أن تكون نهائية ولن يقبل أي تخفيض في الأسعار من العارضين تحت طائلة اتخاذ الإجراءات القانونية بحق العارض . 9- يعتبر العارض المتقدم بعرضه للشركة السورية للغاز قد أحاط علما"بالقوانين والأنظمة المطبقة في الجمهورية العربية السورية . 10- الضمانة : 10-1- يضمن المتعهد جودة ونوعية التوريدات والمواد, و الأعمال والخدمات (المشروع) من حيث التصميم والصناعة والأداء الجيد وتكون هذه الضمانة سارية المفعول لمدة سنة اعتبارا من تاريخ إنجاز الأعمال وتسليمها استلاما" مؤقتا" . 10-2- يلتزم المتعهد خلال فترة الضمان المذكورة باستبدال جميع المواد المعيبة بمواد جديدة وإيصالها حتى موقع العمل و تركيبها على نفقته. 10-3- يلتزم المتعهد خلال فترة الضمان المذكورة آنفا بناء على طلب خطي من الإدارة أن يصلح أو يبدل مجانا وبدون تأخير جميع الأعطال الناشئة عن الأعمال التي تم تنفيذها من قبله وكذلك القطع التبديلية التي قام بتركيبها . وتخضع هذه المواد الجديدة ( المستبدلة) إلى فترة ضمان جديدة مدتها سنة من تاريخ الاستبدال . 10-4- في حال عدم استبدال المتعهد للمعدات المعيبة خلال فترة معقولة تحدد من قبل الإدارة , يحق للإدارة استبدال هذه المواد على نفقة المتعهد 10-5- إ ذا ظهر بعد فترة الضمان عيب في الصنع أو عيب تعمد المتعهد إخفاءه ,يبقى الضمان ساريا لمدة سنة اعتبارا من تاريخ تلافي هذا العيب. 11- التأمين : 11- 1 يلتزم المتعهد بالتأمين على التوريدات إلى موقع العمل في الجمهورية العربية السورية على نفقته. 11-2 يجب على المتعهد الحصول على نفقته على بوليصة تأمين ضد جميع الأخطار (تسمى البوليصة) و الاحتفاظ بها و ذلك فيما يتعلق بالمشروع و المواد والمعدات اللازمة لتنفيذ العمل. 11-3 تحتجز البوليصة لمصلحة الإدارة وتظهر فائدتها على البوليصة و تسلم نسخة مصدقة أصولاً إلى الشركة السورية للغاز . 11-4 تغطي بوليصة التأمين المشروع و كافة المواد و المعدات و التوريدات اللازمة لتنفيذ الأعمال و ذلك ضد جميع الأخطار المؤمن ضدها بموجب تلك البوليصة وحتى انتهاء الاستلام المؤقت للمشروع وشاملا يوم الاستلام المذكور. 11-5 يؤمن المتعهد و المتعهدون الثانويين وعلى نفقتهم الخاصة ، على مستخدميهم وفقا لمقتضيات القانون السوري . 12- تدفع التأمينات المؤقتة أو النهائية كما يلي : 12-1 يكون أداء التأمينات المؤقتة والنهائية إما نقداً يدفع في صندوق الشركة السورية للغاز بحمص أو في حسابها المصرفي المفتوح لدى المصرف التجاري السوري بحمص فرع / 1 / برقم / / أو كفالة أو حوالة مصرفية أو شيك مؤشر عليه بالقبول ( شيك مصدق) من المصارف المقيمة المعتمدة من الجهات العامة المختصة في الجمهورية العربية السورية. 13-الكفالات المصرفية -كفالة حسن التنفيذ: 13-1 يجب أن تصدر جميع الكفالات المصرفية الواجب على المتعهد تقديمها بموجب العقد عن مصرف يقبله المصرف التجاري السوري الفرع رقم /1/ - حمص بناء على طلب المتعهد وعلى حسابه و يجب أن تعزز هذه الكفالات من قبل المصرف التجاري السوري. و أن تصاغ حسب النموذج المعتمد من قبل المصرف التجاري السوري فرع رقم (1) بحمص. يدفع المتعهد كافة الرسوم و الطوابع والنفقات المترتبة على تعزيز و تمديد هذه الكفالات إلى المصرف التجاري السوري رقم /1/ في حمص. 13-2 يقدم المتعهد خلال /15/ يوما من تاريخ فاكس التثبيت كفالة حسن التنفيذ بواقع 10% ( عشرة بالمائة) من قيمة الإحالةتحت طائلة اتخاذ الإجراءات القانونية بحقه. تحرر كفالة حسن التنفيذ هذه و ينتهي مفعولها بعد انتهاء فترة الضمان و بعد ثلاثون يوما من تاريخ إصدار شهادة الاستلام النهائي موقعة من الإدارة وبعد الحصول على براءة ذمة من الدوائر المالية ولا تعتبر إنهاء للمسؤولية. 14– تعديل العقد: - يحق للإدارة زيادة الكميات المتعاقد عليها أو إنقاصها خلال مدة تنفيذ العقد بنسبة لا تتجاوز 30% لكل بند أو مادة من العقد على حده و ذلك بنفس الشروط و الأسعار الواردة في العقد و دون حاجة إلى عقد جديد على أن لا تتجاوز قيمة مجموع الزيادة أو النقص 25 % من القيمة الإجمالية للعقد، و لا يحق للمتعهد المطالبة بأي تعويض لقاء ذلك, و ذلك خلال مدة سريان الاعتماد. - يعطى المتعهد في حال الزيادة مدة إضافية تتناسب مع طبيعة و مقدار هذه الزيادة و ذلك من أجل هذه الزيادة فقط. 15- لا تقبل العروض المقدمة إلا من إحدى الفئتين التاليتين : - المصنع أو المجمع للأجزاء الرئيسية من التجهيزات , الذي نفذ مشاريع مماثلة . - ائتلاف شركات يكون أحد أطرافه مصنعاً أو مجمعاً للأجزاء الرئيسية من التجهيزات المذكورة و أن يكون قد نفذ أيضاً مشاريع مماثلة. 16- يجب أن يرفق بالعرض المقدم من المصنع أو المجمع على النحو المذكور , الوثائق التي تثبت تنفيذه بنجاح مشاريع مماثلة. 17- يجب أن يرفق بالعرض المقدم من ائتلاف شركات , الوثائق التالية : - نسخة عن اتفاق الائتلاف مصدقة من المراجع المختصة موضحاً فيه اسم الممثل المفوض من الائتلاف0 - الوثائق التي تثبت تنفيذ أحد أطراف الائتلاف بنجاح , مشاريع مماثلة0 و تقدم كفالة التأمينات المؤقتة باسم أطراف الائتلاف جميعاً , و يعتبر هؤلاء مسئولين أمام الإدارة أو الجهة المتعاقدة صاحبة المشروع بالتكافل و التضامن عن عرضهم . 18- إذا اعتبر العرض المقدم من ائتلاف شركات هو العرض الأنسب لمصلحة الإدارة أو الجهة المتعاقدة , يوقع العقد من أطرافه مجتمعين ، أو من يمثلهم أصولاً ، و يعتبر هؤلاء مسئولين أمام الإدارة صاحبة المشروع بالتكافل و التضامن عن تنفيذ الالتزامات العقدية و تقدم كفالة التأمينات النهائية في هذه الحالة ، باسم الائتلاف وفقا ًلعملات العقد . 19- على المتعهد المرشح توقيع العقد خلال مدة لا تزيد عن/ 15/ خمسة عشر يوما" من تاريخ تبليغه الإحالة , وفي حال عدم حضوره أو امتناعه عن توقيع العقد يعتبر ناكلا" وتصادر التأمينات المقدمة من قبله ويحق للإدارة مطالبته بتعويض عن العطل والضرر. 20-حل الخلافات: يتم حل الخلافات وفق المادة /66/ فقرة ( أ- ب ) من القانون رقم /51/ لعام 2004. أ – القضاء الإداري في الجمهورية العربية السورية هو المرجع المختص للبت في كل نزاع ينشأ عن العقد . ب – يتم اللجوء إلى التحكيم وفقاً للأصول المتبعة أمام القضاء الإداري. 21- شحن و نقل و تخليص التوريدات المتعاقد عليها : يقع على عاتق المتعهد عبء شحن و نقل و تخليص التوريدات المتعاقد عليها من المصانع حتى مواقع العمل( سيف) ويستثنى من التعليمات الواردة في الباب الثاني الفصل الأول من المرسوم 450 لعام 2004 المتعلقة بشروط النقل والتامين . يتولى المتعهد رعاية الأجهزة الخاصة بالشركة عند تخليصها من الحدود السورية و من ثم يتولى كامل المسؤولية عن هذه الأجهزة بما في ذلك أمور الشحن و النقل و التخزين الآمن من أي ضرر قد يصيب الأجهزة و يجب على المتعهد التقيد بتغليف التوريدات قبل الشحن وفقا للقواعد الدولية المتبعة في النقل البحري و البري و الجوي و كل ضرر يصيب التوريدات من جراء تغليف غير كاف يقع على عاتق المتعهد. 22- يتم تحويل مبالغ العروض المقدمة بعملات أجنبية أخرى قابلة للتحويل إلى الدولار الأمريكي وفق الوسطي لنشرة الأسعار الرسمية لمصرف سورية المركزي بتاريخ فض العروض المالية أو أقرب تاريخ ليوم فض العروض المالية. 23- يمكن أن يقدم العارضون المهتمون بتمويل المشروع عرضاً مالياً خاصاً ، و الذي سيؤخذ بعين الاعتبار عند تقييم عروضهم، يجب أن يوضع هذا العرض الخاص في مغلف مغلق ضمن العرض المالي ( المغلف الثالث) 24- في كل ما يرد عليه النص يرجع إلى نظام العقود الصادر بالقانون رقم /51/ لعام 2004 ودفتر الشروط العامة الصادر بالمرسوم رقم /450 /لعام 2004 | In pursuance of the Law No.51 of 2004 including contracts system, especially Section four (call for Tenders). First Article: First - Contract Documents: The following items are considered as an integral part of our general and special conditions: 1-The contract system issued under the Law No.51 of 2004 2-The general Tender Book issued under the Law/450/ of 2004. 3-The special technical, financial and legal Tender Book. 4-The model contract issued by the Cabinet attached to the file. 5-Advertisement for T/File NO /2025. Second- Project Definition: Means the design, procurement supply and construction and all work specified in the Technical Tender Book (On Turn Key Bases) for the Arab Gas Pipeline Project Phase II are located at pipeline rout, which shall connect to Arab Gas Pipeline Project Phase I at AL Foreqls area (about 50 km east of Homs City) at BVS 6011 , extended to Aleppo PRMS(R-7003 )with length about /186/km. Second Article : Special Provisions: a-Providing Bid Bond for USD (5000000) only five million US Dollars. b-Execution Period ( ON TURN KEY BASES): Contractor will undertake to execute the whole project during / 22 / twenty two months from the commencement order , according to this contract and its technical exhibits (Contract Scheduel) exhibit /D/. c. The commencement order shall start within /7/ seven days from the date of the receipt by Contractor the notification of opening the confirmed letter of credit by the Administration d -Performance Bond: 10% P/B out of total order value during /15/ days from placing order . e-closing date : End of official working hour of: / /2025 . f- Partial quotation: Is unacceptable. g- The place for receiving offers: offers submitted at SGC in Homs , ,POBox/4499/ Tel./00963-12—21496108-2496101 / Fax. /00963-12-2496640 / Third Article: The offer should be presented in three numbered and sealed envelopes to be put into fourth envelope addressed to: Syrian Gas Company – Contracts and Purchasing Directorate ,indicating: 1-S.G.C File Number. 2-Subject of File. 3-Closing date of the file . 4-Name of bidder company and its nationality. 1) The First Envelope Contains: 1-1 Documents proving that the bidder company is one of the companies specialized in carrying out such works as defined in Technical Tender Book according to Annex A para /2/ instructions for bidder Item /2-10/ offering the bid. 1-2 The foreign bidder should adhere to nominate commercial agent in Syrian Arab Republic, his agency should be registered at competent authorities in accordance with the Rules of Legislative Decree no.151 , of 1952 and its amendments within stipulated conditions and rules, and the rules of decree no.15 of 2001 . 1-3 Declaration by the Bidder that he is acquainted with General and special Tender book ( Legal, Technical and Financial) and with supplies and required activities relevant to the Tender and he should adhere to all the provisions and rules mentioned in these documents. 1-4 Chosen Domicile: a- The bidder has to define his chosen domicile in Syrian Arab Republic and his detailed address. b- - The Arabic Bidder and The foreign bidder who is not residential in Syria may determine his chosen domicile to be outside Syrian Territories. The contractor should adhere to this address even if he moved to another one unless he informs the administration by written notification about his new domicile in the same country. Otherwise, all corresponded notifications to the contractor in his first chosen domicile are regarded legal . 1-5 the bidder adherence that the materials and which will be supplied and mounted in the project are new, not renewed. 1-6 Declaration by the bidder clarify that he does not have a factory, an organization or any subsidiary in Israel, and has not owned shares in any institution or organization in Israel, nor being part in any manufacturing, assembly, licensing or technical assistance contract with any institution, organization or person in Israel, nor engaging in any of such activities by himself or by mediator, and has no contribution in supporting Israel or its military efforts. 1-7Notification of Bid Bond settlement, according to Article /7/,paragraph /12/. 1-8 the bidder should not be forbidden from participating in tenders or from contracting with the government bodies or has any provisional or executive liens on behalf of (governmental) general parties . 2) The Second Envelope Containing : The technical offer for required works according to the technical Tender Book And it is not allowed to include any prices , reserves , financial or legal conditions and will not be considered of any of above mentioned subjects, if it was included. . 3) The Third Envelope Containing: The financial offer with the unit and total price lists for required activities ,equipments , materials and spare parts according to Technical Book (On Turn Key Bases) and should be prepared by the bidder clearly without any scratch, rub or insert and should not include any prices, reservations, or legal and financial conditions and will not be taken into consideration if mentioned. Provided those prices should be stated according to price breakdown stated in Annex /A / pages (4 – 25) of Technical Tender Book. Fourth Article : The bidder has to submit a statement with his technical offer in which he undertakes that the spare parts which will be supplied for the Project are original and guaranteed in compliance with the applied technical standards of the manufacturing companies for these materials. Fifth Article : The offer will be rejected in the following cases : 1-In case the bidder does not adhere completely to financial and legal T/Book and to the contract draft . 2- Registering the offer in SGC registration offices after the closing date 3-In case B/Bond is not received within the closing date. 4- in case submitting the offer in away violate the rules of the contract system issued by Law /51/of 2004. Sixth Article: Tax And Duties : 1-The contractor shall bear the following taxes and duties: 1-1 Contract stamp and fees in a ratio /0.008/ of the total contract value plus fiscal stamp value amounting to 1 $one USD or its equivalent of the offered currency; to be paid within ten days from the date of notifying the Beneficiary of L/C for the first time by the correspondent bank . 1-2 Advertisement charges with the value of about $ 600 USD ,or its equivalent of the offer’s currency , to be deducted from L/C value . 1-3 All duties and fees incurred on legalization of documents from Syrian Embassies or Syrian Missions outside Syrian Arab Republic . 1-4 All taxes and duties imposed out side Syrian Arab Republic . 1-5 Expenses of L/C and/or import license amendment and re-export, in case he causes such amendments. 1-6 All expenses of issuance and extension of bid bonds and performance bonds . 1.7 All expenses of custom clearances except custom fees. 1-8 Expenses of inspection certification which issued by a neutral international inspection company Chosen by the administration from the list or lists which will be nominated by the contractor. 2) Syrian Gas Company Shall Bear The Following costs: 2-1-All taxes and fees imposed inside Syrian Arab Republic Territory resulting from executing this contract and are not included in paragraph/1/Article /6/. 2-2- Customs duties inside Syrian Arab Republic. 2-3 Expenses of opening and confirmation of Letter of Credit , according to the contract conditions and expenses of L/C amendment in case the administration causes it. 2-4 Expenses resulted of agricultural damages and possessing lands within the pipeline district determined in Technical Tender Book only. Seventh Article : General Provisions : 1- Only one offer is accepted from the bidder, and the previous registered offer in the company's registration offices is authorized ( only one option). 2-Each offer is considered valid for 180 days after the closing date . It will be automatically extended after the expiry period for further 180 days, unless the bidder has submitted a written request to withdraw his offer within the first 7 days from expiry of 180 days. When placing the order with the company which got the offer , then the said company should keep the validity of its offer for /6/ six months starting from the date of issuing the guarantee of good execution ( performance bond) in addition to the period between the date of placing the order and issuing the performance bond. After the expiry of six months, the company which got the offer has the right to withdraw her offer within /7/ days from the date of expiry of this period , otherwise , the validity shall be extended automatically for another six months and so on . 3- Major Force: In case of major force , the laws and regulations valid in Syrian Arab Republic will be applied provided that Syrian Gas Company should be informed of the major force by written letter, or fax message within /15/ fifteen days from major force event date. The contractor should present official document legalized by the Chamber of Commerce and the Syrian Embassy in the country where the major force has occurred, for proving such . Otherwise, the contractor will not have the right to ask for delivery period extension and for objection about payment of delay penalty. 4- Delay Penalties: Delay penalty shall be calculated as one per thousand of total contract value for each day of delay in execution the contract , but not exceeding 20% of total order amount. Delay penalties could be calculated according to the part delayed in execution providing that the following two complementary conditions are fulfilled: A- The other achieved works should be submitted within the originally specified execution periods. B_ The delayed part should be independent in normal use from the achieved works and does not affect the operation of the project . 5- Down Payment and Payment Method : Payments are carried out as follows: 5-1. Down Payment: 10% ten percent of the foreign currency portion shall be paid as down payment in foreign currency: i.e: - the amount of USD: - and the amount of /100000000/ SP only one hundred million Syrian Pound shall be paid as down payment in Syrian currency. Against bank guaranty presented by the Contractor to the Administration which is equivalent to the down payment . this guaranty should be issued or confirmed by Commercial Bank of Syria Homs branch No. / 1/ . acc to the form stated by the bank, provided that this down payment should be paid after the commencement order. 5-2 Payment Method : - the foreign currency portion shall be paid for equipment and materials and services, transport costs, erection, licenses, insurance, design costs, etc............., will be paid as following: 5-2-1 sixty five percent (80%) of the foreign currency portion shall be paid to the Contractor against shipping documents of the equipment and materials on the basis of (CIF site) presented by the Contractor, as indicated in Para 10.4.1 ( of the attached typical contract) by means of an-irrevocable and divisible and confirmed Letter of Credit opened in hard currency by the Commercial Bank of Syria No. (1) in Homs in favor of the Contractor. The Contractor will be notified of This L/C by the means of the Corresponding Bank to CBS. 5-2-2- four percent (5 %) out of the foreign currency portion will be paid to the Contractor, for the services outside SAR against the documents which shall be presented by the Contractor as indicated in para 10.4.2 by means of an irrevocable and divisible and confirmed L/C, opened in foreign currency by Branch No. 1 in favour of the Contractor. This L/C is to be notified to the Contractor by the corresponding bank of the CBS. - Thirty one percent (15%) out of the foreign currency portion, shall be paid to the Contractor, as monthly payment against the progress of installation work, civil works and other charges in Syria, by means of irrevocable divisible and confirmed L/C, opened in foreign currency by CBS, in favour of the Contractor. This L/C is to be notified to the Contractor by the corresponding bank of the CBS. 5-2-4- The local currency portion : An amount / 1000000000 /S.P only (one billion ) Syrian pounds. shall be paid to the Contractor as monthly payments, against submitting progress reports approved by SGC site representative(s) and administration by bank transfer or check to contractor ‘s account in Syria. The Contractor shall submit his financial offer only in USD or exchangeable foreign currency, the local currency will added to the bidder financial lump-sum offer. 5-3 The Contractor shall issue all his invoices for all the components of the Contract’s value on the basis of total invoice value (i.e. 100% hundred percent of invoice value ) it should also clearly show the following deductions A- 10% (ten percent) of the total value of every invoice will be deducted against reimbursing the down payment, paid according to Art. 9 arr. of the Contract. B- five percent (5%) of the total value of every invoice will be deducted, as stoppage, shall be paid against the issuance of the Mechanical Completion Certificates (MCC) by the Administration, by cable bank transfer to the Contractor’s account within (40) forty days from the issuing date of (MCC) C- five percent (5%) of the total value of every invoice will be deducted, as stoppage, shall be paid against the issuance of the provisional acceptance Certificate (PAC) by the Administration, by cable bank transfer to the Contractor’s account within (40) forty days from the issuing date of (PAC). D- deduct the agent commission according to percents specified in his commercial agency from the invoices. i.e. the invoice shall show clearly the full value of the invoice and the remaining payable amount of that value. 6- The contract shall include the following text : The Contractor shall have the right of withdrawal the contract without having the right to claim compensation for any defect or damage in case the Administration has not opened the L/C within /6/ six months from the date the Contractor being notified of the ratification of the contract and be considered valid . In case the Bidder does not ask for withdrawal the contract within one week from the expiration of the six months, the bidder's obligations will automatically be extended for another six months, and so on . 7- Revocation of the contract and cancellation the excution according to rules of Article No.(54-55-59-60) of the Law no. /51/ of 2004. 8- Prices submitted by the bidders should be final, any price reduction cannot be accepted by the bidders , under Legal proceedings that the bidder will be deprived from contracting . 9- The bidder who participated in SGC tenders shall be considered acquainted with all laws and regulations applied in Syrian Arab Republic . 10- The Warranty : 10-1- The contractor shall warrant goodness and high quality of materials, activities and services concerning design, manufacturing and performance. This guarantee is valid one year from the date of executing works and delivering them temporarily . 10-2- The contractor , during the Period of a.m. warranty period, shall adhere to replace all defected materials with new ones and have them transported to the worksite, and to be installed on his own account . 10-3 - The contractor undertakes during the a.m. warranty period, under a written request by the Administration , to repair or replace, free of charge, and without delay, all defects resulting because of works executed by him , and the spare parts he had installed . The new materials (replacement) shall have another warranty, for the period of one year starting from the date of replacement. 10- 4 In case the defected materials were not replaced by the Contractor within a reasonable period; to be defined by the Administration , the Administration shall have the right to replace these materials on the contractor's account. 10-5- If it appears, after expiry of the warranty period, any manufacturing defect that the contractor has concealed intentionally, the warranty period shall be valid for further one year beginning form the date of this defect correction. 11- Insurance : 11-1-The Contractor shall adhere to provide insurance on all procurements and materials to the work site inside Syrian Arab Republic territories on his account. 11-2- The Contractor shall at his expense obtain and maintain a Contractor’s “All Risk Insurance Policy ” (The Policy) in the respect of the Project and all materials, equipment and supplies required for the execution of the Work. 11-3 The Policy shall be held for the benefit of the Administration, and its interest shall be endorsed on the Policy, and an officially legalized shall hand over to Syrian Gas Company . 11-4 The Policy shall cover the Project and all materials, equipment and supplies required for the execution of the Work, against all risks up to the date Provisional Acceptance of the Project, including completing the receipt day . 11-5 The Contractor and the sub-Contractors shall, at their expense, insure their employees according to the requirements of the Syrian law. 12 - Bid or Performance Bond To Be Paid As Follows: 12-1- Cash paid in Syrian Gas Company Box in Homs or to SGC bank account at the Commercial Bank of Syria Branch/1/in Homs with no. / /or by A bank guarantee ,bank transfer or by an acceptable Cheque certified by one of the Syrian resident banks in Syrian Arab Republic. 13-Bank Guarantees, Good Execution Guarantee : 13-1 All bank guarantees; to be provided by the Contractor under the Contract, shall be issued by a bank accepted by the Commercial Bank of Syria, Branch. No. (1) Homs, at the request of the Contractor and on his account, and should be confirmed by the CBS. They shall be in the form approved by Commercial Bank of Syria, Branch No. (1) Homs. The Contractor shall pay all Stamp duties, fees and expenses; charged or occurred because of the confirmation and extension of these Guarantees, to the CBS, Branch No. (1) Homs. 13-2 The contractor shall provide, within /15/ fifteen days from the date of fax of confirmation good execution, guarantee to the value of 10% (ten percent) of the Lump Sum of the total order value. The good execution guarantee will be released and terminated after the end of guarantee period and 30 days after issuing the final Acceptance Certificate signed by the Administration after having an quittance security from the financial directorate and this will not considered as termination for his responsibility 14- Contracts' Amendment a -The Administration has the right to increase or decrease the total quantity of this Contract at the rate of 30% for each item separately with the same prices and conditions mentioned in this Contract with no need to organize a new Contract, provided the Total value of increases and decreases should not exceed 25% of the Total Amount of the Contract, The Contractor shall not claim for any Indemnification against this within the period of L/C validity. b- In case of increases the contractor granted an additional period appropriate for the nature and amount of this increase, and that for the increase only. 15- Only one of the two following categories of The submitted offers would be accepted: 1-The manufacturer or the collector of the equipments main parts who has executed identical projects . 2 –A coalition of companies , one of which is the manufacturer or the collector of the equipments main parts who also has executed similar projects . 16- Documents proving its successful execution of identical projects should be accompanied by the offer submitted by the manufacturer or the collector . 17-The following documents should be accompanied with the offer submitted by the coalition of companies: a- A copy of the coalition agreement ratified by specialized authorities , clarifying the name of the authorized representative by the coalition. b- Documents proving the successful execution of identical projects by one of the coalition’ s party. A guarantee of provisional bonds should be submitted in the name of all the coalition parties, and they considered responsible for their offer by joint liability ( jointly and severally) in front of the administration or the contracted party who executed the project. 18- If the offer submitted by the coalition of companies is the fittest for the benefit of the administration or the contracted party , it must be signed by all the gathered parties or by their duly representative , and they are responsible for executing the contracted obligations by joint liability( jointly and severally) in front of the project’ s administration In this case ,and in the name of the coalition ,a guarantee of performance bond is submitted according to the contracted currencies 19- The nominated contractor has to sign the contract within /15/ fifteen days from the date of being notified the placing order date . In case he does not attending or refusal to sing the contract, then he will be considered abstainer and his bond will be confiscated, and the Administration has the right to claim him in compensation for the lose and damage. 20- Settling Disputes disputes shall be resolved according to Article /66/ para. (a-b) of Law no. /51/ of 2004 a- The Syrian Administrative Jurisdiction is the content authority to resolve every dispute may arise out of the contract. b- It would referred to arbitration according to the rules taken in front of Administrative Jurisdiction. 21-Shipping Transporting and supplies clearance: The Contractor shall be responsible for shipping, transporting and clearing the contracted supplies from the plants to the job-site (CIF) and will be exempted from the section one part two of the general Tender Book issued under the decree/450/ of 2004 regarding the regulation of transportation and insurance. The Contractor shall take custody of Company’s supplied equipment when it clears at Syrian border, and then have full responsibility for this equipment including handling, transportation, safe and secure storage. The Contractor has to pack these supplies before shipping according to the applicable International rules for maritime , terrestrial and aerial transport. Any damage that may occur to the supplies, due to unsatisfactory packing, shall be the responsibility of the Contractor. 22- the financial offers submitted in foreign currencies will be exchange to USD according to the USD average price in the official sheet of prices issued by the central bank of Syria on the date of the financial evaluation or nearest date. 23- Bidders who are interested in financing the project can submit a special financing offer which will be considered in the evaluation of their bids, this special offer should be put in a closed envelope in the financial offer (third envelope). 24- The reference of this text is the contracting system issued by Law /51/ of 2004 and Technical Tender Book issued by Doctrine no. /450/ of 2004. |
| --- | --- |
| المدير العام |  |