SCHEDULE PEA:  PROJECT EXECUTION AND ADMINISTRATION

TABLE OF CONTENTS

PART A - PROJECT EXECUTION.

1.0	CONTRACTOR’s PROJECT EXECUTION COMMITMENTS.

2.0	DESIGN/ENGINEERING.

2.1  Basic Design Review.

  - Hazard and Operability Study (HAZOP).

  - Detail Design

3.0	PROCUREMENT.

3.1  CONTRACTOR's Procurement Commitments.

3.2  Delivery and Transport.

4.0 	CONSTRUCTION.

5.0 	PRECOMMISSIONING, COMMISSIONING AND ACCEPTANCE TESTING.

5.1  Precommissioning.

5.2  Introduction of Process Media.

5.3  Commissioning.

5.3.1	General.

5.3.2	Commissioning.

5.3.3	Ready for Acceptance Testing.

5.3.4	Acceptance Tests.

5.3.5	Issue of "Certificate of Provisional Acceptance of the WORK".

5.3.6	Hand-over.

6.0	Deleted

7.0	WARRANTY.

8.0 	ISSUE OF "CERTIFICATE OF FINAL ACCEPTANCE OF THE WORK".

9.0 	SPARE PARTS, SPECIAL TOOLS, TESTING EQUIPMENT & OPERATING

SUPPLIES.

9.1 Spare Parts.

9.1.1	General.

9.1.2	Start Up and Commissioning Spare Parts.

9.1.3	Normal Operation.

9.1.4	Spare Parts List and Interchangeability Record (SPIR) Forms.

9.1.5	Ordering for Normal Operation.

9.2  Special Tools and Testing Equipment.

9.3  Operating Supplies.

10.0	Deleted

11.0 CONTRACTOR’S ON-SITE FACILITIES AND SERVICES.

11.1 Security.

11.2 Sanitation.

11.3 Project Signboards.

11.4 Vendor Representatives.

11.5 Facilities and Services for COMPANY's Representative on-Site.

11.5.1 Office, Furnishings, Equipment, Assistance and Services.

12.0  SUB-CONTRACTING

PART B - PROJECT ADMINISTRATION

1.0	CONTRACTOR DOCUMENTATION REQUIREMENTS.

2.0	CONTRACTOR SCHEDULING REQUIREMENTS .

2.1  Schedule Format

2.1.1 Precedence Network.

2.1.2 Barchart.

2.1.3  Manpower Histogram

2.2  CONTRACTOR's Scheduling Commitments.

2.2.1  Contract Implementation Schedule.

2.2.2 Site Construction Schedule.

2.3  Left blank.

2.4  Testing Schedules.

2.4.1 Test Schedule for CONTRACTOR Procured Equipment/Materials.

2.4.2 Test Schedule for On-site Pre-Commissioning.

2.5  Commissioning Schedule.

2.6  Tie-In Schedule.

2.7  Completion and Handover Schedule.

3.0 	REPORTING.

3.1  Progress Reporting.

3.2  Weekly Reports.

3.3  Weekly Progress Meetings.

3.4  Monthly Progress Report.

3.5  Management review meetings.

4.0 	CONTRACTOR PREPARED INFORMATION.

4.1  Organisation Chart.

4.2  CONTRACTOR's Management and Supervision Personnel.

4.3  Quality Control.

4.3.1 Quality Plan

4.4  Health, Safety and Environment (HSE) Plan.

4.5  Transportation Plan

4.6  Schedule of CONTRACTOR's Submittals.

4.7  Permit To Work (PTW) System(s).

4.8  Contract Documentation.

4.8.1	Document Control

4.8.2	Calculation Books.

4.8.3	Manufacturer's Data Books.

4.8.4	Pre-Commissioning and Commissioning Manuals.

4.8.5	Start-up Manual.

4.8.6	"As Built" Drawings.

4.8.7	Operation and Maintenance Manuals.

4.9   Drawings.

4.10 Samples.

APPENDICES:-

1.	UNITS OF MEASUREMENT;

2.	DRAWING NUMBERING SYSTEM;

3.	PACKINGINSTRUCTION

4.	SPARE PARTS DOC. & PURCASIN AND GGUIDE TO COMPLETION OF THE SPARE PARTS LIST AND INTERCHANGEABILITY RECORD (SPIR);

6.	MONTHLY SAFETY REPORT FORMAT;

7.	SCHEDULE OF CONTRACTORS SUBMITTALS;

- OPERATING SUPPLIES.

PART A - PROJECT EXECUTION.

1.0	CONTRACTOR’s PROJECT EXECUTION COMMITMENTS.

CONTRACTOR SHALL execute WORK with promptness and diligence in order that the WORK should be completed within the CONTRACT Schedule time (Exhibit-D). The CONTRACTOR’s work responsibilities SHALL be performed in accordance with this Schedule PEA except as amended or revised in all Exhibits and appendice of this tender book or/and correspondances of bid evaluation stage.

2.0	DESIGN/ENGINEERING

2.0.1 Kick-off

Within two weeks of CONTRACT’s commencement, a kick off meeting will be held in COMPANY’s offices. CONTRACTOR will attend this kick-off meeting with his senior technical discipline engineers.

Design/Engineering SHALL include, but not be limited to, specified bellow and stated in the technical scope of work of tenedr documents:

(I) 	the development of the engineering design for the facilities as described in Exhibit 'B', based on the parameters, data and information provided in all Exhibits and this Appendixs of this schedule .

(ii)  	the performance of design studies, site surveys &  investigations and calculations and 	associated tests;

(iii) 	the updating and revision of all those existing drawings, which are applicable to, and/or affected by, the installation of the facilities as described in Exhibit 'B', Scope of Work.

Immediately after CONTRACT commencement, CONTRACTOR SHALL advise, which existing drawings or data CONTRACTOR needs.

COMPANY does not guarantee the availability of any drawing unless specifically stated in writing elsewhere in the CONTRACT.

COMPANY does not guarantee the accuracy of the existing drawings supplied by COMPANY.

CONTRACTOR is responsible to verify ''as-built'' conditions for existing drawings and modify drawings as appropriate.

CONTRACTOR SHALL include timing for as-built modifications of existing drawings in the CONTRACT implementation schedule.

The as-built revisions SHALL be issued to COMPANY prior to the basic design review.

(iv)	the preparation of new drawings and revision of existing and new drawings to "as built" status; all "as built" drawings SHALL be carried out on Autocad Latest version and based on the numbering system provided in Appendix "2" of this schedule.

(v) 	the preparation of specifications, procedures, data sheets, equipment and parts lists.

(vi)	the selection of materials and equipment, and evaluation of vendor information and drawings.

(vii)	CONOPS and Tie-In Plan For each of the facilities as covered by Exhibit B. COMPANY requires that the shut-down period(s) during tie-in of the new facilities are kept to a minimum. CONTRACTOR SHALL present for each of the items requiring tie-in a detailed proposal and time schedule for the tie-ins with the existing plant (mechanical, electrical and instrumentation etc.).

CONTRACTOR SHALL indicate which part of the facilities need to be shut-in, at which date and for how many hours.

(viii)CONTRACTOR SHALL submit as part of the detailed design a full materials take-off. CONTRACTOR SHALL indicate whether materials will be purchased locally in Syria or whether CONTRACTOR intends to import materials into the country (as per CONTRACT’s Vendor list).

The above list will form the basis for obtaining approval for material importation into Syria.

(ix)  	COMPANY SHALL review and comment on all engineering and design deliverables.

CONTRACTOR SHALL submit the relevant documents for review. As a minimum COMPANY will review the schedules, the basic design package (including the design book), the detail design drawings, the purchase orders, the pre-commissioning and commissioning manuals, the pre-commissioning report and punchlist, the operating and maintenance manuals, SPIR forms, the QA and HSE manuals, the 72 hr. test program and report.

CONTRACTOR SHALL give COMPANY opportunity for such reviews and comments before taking irreversible action or making significant monetary commitments, such as purchase orders and subCONTRACTs.

CONTRACTOR SHALL present documents to COMPANY in a timely manner and in a logical sequence. CONTRACTOR SHALL respond to COMPANY's comments, if any, before taking further action.

CONTRACTOR SHALL submit engineering deliverables for COMPANY's review in five (5) fold (tow copy of all submittals shall be delivered to the Consultant, with which Company shall be contracted to review and approve the design activities and documents and supervise the construction works of the project), unless specifically stated otherwise, and SHALL conform with the RFQ requirement.

The "Reviewed" issues will include all COMPANY comments, unless agreed otherwise in writing.

CONTRACTOR will issue COMPANY with a complete detail design package prior to commencement of field construction activities.

CONTRACTOR SHALL issue three (3) copies of the complete design package at least in eight (8) ring binders, one per discipline (Mechanical, Instrumentation/Control & Telecommunication, Civil, Electrical, Pipelines, Cathodic Protection, Welding & Coating,).

One week after successful completion of the 72-hr. test, CONTRACTOR will issue the final (as-built) engineering package in a similar fashion.

- Final issues drawings to be stamped "AS BUILT".

CONTRACTOR SHALL include the catalogue of the as-built drawings files with the drawing issue, together with the discs/CD-ROM containing all the relevant files."

2.1	Basic Design Review.

Upon completion of CONTRACTOR's "For Review" issue of Basic Design Package, COMPANY SHALL conduct a Basic Design Review. The Basic Design Package will typically include, but not limited to, the following:

Process:

- PFD's and  P & ID's

- heat and material balances

- process model and process calculations and a summary of process

calculations

- sizing calculations of all vessels

- flare/vent backpressure calculations (including all relief cases considered)

- flare/vent radiation calculations

- depressuring calculations

- cause and effect diagrams

Instrumentation:

- P& ID's

- Cause and effect diagrams

- Functional logic diagrams

- EMCS and ESD systems architectural diagrams

- List of alarm and trip settings

- Anti surge system

- Operating control & safeguarding philosophy

- Purchase orders/data sheets for:

EMCS system

ESD system

control valves

PSD/ESD valves (including depressuring valves)

relief valves

instrument air/gas system

- Control room layout

- Plotplans (main equipment and main cable routes)

- Calculations for instrument air usage, UPS requirements, control valves

- A summary of instrumentation documentation and  drawings

Electrical:

- single line diagrams

- plotplan and cable routing drawings

- MCC building and switchgear lay-out

- protection block diagram, c.t ratios

- the following calculations

- system loadflow calculations

- short circuit calculations

- continuous and short circuit current carrying capacity of all electrical equipment

- mutiplexer/demultiplexer equipment

- intertripping and interlocking proposals

- utility data sheets

- mimic panel details

- annunciator panel details

- data sheets for:

- transformers

- dc supply units

- switchgear

- control and monitoring panel details

- overhead lines

- fibre optic signalling system.

Mechanical:

- PFD's and P & ID's

- purchase orders/data sheets for:

- all equipment

- all pumps performance data and curves

- inspection and test plans (per equipment)

- all vessels

- filters

- chemical injection packages

- instrument air/gas package

- plotplans

-	calculations for:

- NPSHA and NPSHR for pumps

- pump power calculations

Civil:

- plotplan/survey plan (including drainage plan)

- lay-out of the MCC building

- calculations for:

- design/construction MCC building and control centre

- Building and control room air conditioning requirement

- purchase order for:

- the buildings air conditioning

- road drawings

Pipelines:

- proposed Gas trunkline, gas line routing

- pig launcher/receiver drawings

- P and ID's

- plotplans (showing entry and tie-ins)

- cathodic protection systems schematics

- cathodic protection calculations

- location of corrosion monitoring points

- Gas trunkline hold up calculations

- purchase orders for:

- pipeline, including coating, lining for the trunkline

- corrosion monitoring points

- sphere launchers/receivers

General:

a. Area classification drawings.

b. Design book

Three copies of the above package SHALL be submitted to COMPANY office and one copy to Consultant’s office at least three weeks before the schedule date for the Basic Design Review start.

The design review SHALL be undertaken at COMPANY’s offices and SHALL be undertaken by the Senior CONTRACTOR design engineers in conjunction with a review team from COMPANY. The all relevant cost SHALL be part of CONTRACTOR’s CONTRACT prices.

CONTRACTOR is required to indicate in the CONTRACT implementation schedule provided with the Bid documentation when CONTRACTOR anticipates being in a position to undertake the Design review.

The Design Review Report endorsed by the participants SHALL detail the findings of the review and where necessary SHALL be prescriptive on where further CONTRACTOR action is warranted as part of CONTRACTOR’s WORK.

CONTRACTOR SHALL issue the Draft Design Review Report to COMPANY after the Review meeting, detailing the main findings of the Review by Discipline. The Final Report, including copies of reviewed drawings SHALL be issued by CONTRACTOR to COMPANY in due time.

An Action Plan SHALL be issued by CONTRACTOR to COMPANY after the Design Review to detail CONTRACTOR’s follow-up actions and as a record for future audit to demonstrate their incorporation in the WORK.

This SHALL distinguish between items which are agreed by all parties to be items required under the CONTRACT and those items which CONTRACTOR believes are out with the provisions of the CONTRACT.

CONTRACTOR SHALL bear all costs of the Basic Design Review (related to CONTRACTOR staff), even if the duration of the Basic Design Review extends beyond his scheduled duration.

The CONTRACTOR SHALL continue the progress of the PROJECT activities (detail design, procurement etc.) and not holding any activity pending final resolution on the Basic Design Review finding. CONTRACTOR will prepare a formal Basic Design Review close out report, this report will be subject to COMPANY approval.

After completion of Design Review study CONTRACTOR will be obliged to incorporate all actions to the Scope of Work at no additional cost to COMPANY into the design and construction of facilities.

2.2 	Hazard and Operability Study (HAZOP).

On the basis of CONTRACTOR's "Reviewed" issue of PFD's, P&ID's, plotplans, electrical single line diagrams, instrument cause and effect diagrams, area classification drawings, and other applicable drawings, COMPANY will conduct a Hazard and Operability Study (HAZOP).

CONTRACTOR will participate with adequate and sufficiently senior staff to guarantee a successful HAZOP, subject to COMPANY's sole discretion.

The participating CONTRACTOR staff will normally, not be the same as in the basic design review. CONTRACTOR SHALL prepare the HAZOP report.

CONTRACTOR SHALL bear all costs of the HAZOP, even if the duration of the HAZOP extends beyond his scheduled duration.

COMPANY's Representative's conduct of, or failure to conduct, or completion of, or failure to complete, such HAZOP SHALL not relieve CONTRACTOR of any of the responsibilities and obligations of this CONTRACT.

The Final Report endorsed by the Team Leader SHALL detail the findings of the audit and where necessary SHALL be prescriptive on where further CONTRACTOR action is warranted as part of CONTRACTOR’s WORK.

The Final Report SHALL be endorsed by the Team Leader and issued by the end of the review.

An Action Plan SHALL be issued by CONTRACTOR to COMPANY within one week of the HAZOP Review to detail CONTRACTOR’s follow-up actions and as a record for future audit to demonstrate their incorporation in the WORK. CONTRACTOR SHALL report progress against this action plan in the monthly progress reports.

After completion of HAZOP study CONTRACTOR will be obliged to incorporate all actions to the Scope of Work at no additional cost to COMPANY into the design and construction of facilities.  CONTRACTOR should issue a HAZOP close out report, this report SHALL be subject to COMPANY approval.

The updated design package will be issued to the COMPANY within three (3) weeks of the HAZOP review. CONTRACTOR should report progress against this action plan in the monthly reports. The updated design package SHALL be considered “frozen”. Any changes to this package should be subject to COMPANY’s written approval.

2.3	Detail Design

The Detail Design shall include but not limited to the following:

- Platform drawings

- Accessibility details

- Pipe support drawings and details

- Foundation drawing and re baring schedule

- Steel structural details and drawings

- Stress analysis

- Cable tray drawing and details

- Cable list and instrument list

- Instrument hook up drawing and details

- Loop drawings

- I/O list

- Heat tracing and insulation drawing and details.

- isometric drawing

- line list

- Any other typical drawings

COMPANY retains the right to comment on any detail design information.

Other vendor / manufacturing Detail Design like(drawings, calculations and vendor data) will not be subject to COMPANY Review/Approval, however CONTRACTOR SHALL issue to the COMPANY all design information and   typical drawings.

3.0	PROCUREMENT.

CONTRACTOR SHALL procure and furnish all bulk materials, equipment, supplies and spare parts, consumables and services necessary for a complete and operable facility. The handling of all materials and Spare Parts is included in the CONTRACT sum price.

3.1	CONTRACTOR's Procurement Commitments.

CONTRACTOR SHALL prepare a preliminary procurement list, fully consistent with the PROJECT schedules and the Scope of Work. This list SHALL be submitted to COMPANY.

Procurement report SHALL by included in the monthly reports, this report SHALL include as minimum:

- The date of issuing the P.O's.

- Ex-works date

- Required On Site date

- Expected On Site date

- Transportation methods (by air, by sea, ...etc.)

CONTRACTOR SHALL procure and furnish all materials, equipment, supplies, expendables and all other items listed or described in Exhibit 'J' and to the extent permitted in this CONTRACT and SHALL arrange for the acquisition of all subCONTRACTORs.

In connection therewith, and in compliance with other provisions of this CONTRACT, CONTRACTOR SHALL perform all checks and approvals of drawings, specifications, samples and the like, submitted by subCONTRACTORs and vendors, and CONTRACTOR SHALL perform all expediting, inspection and receiving functions.

COMPANY and its Representative reserve the right to review and comment:

(i) 	on the list of  bidders for material, equipment, supplies, expendables and other items 	and subCONTRACTs;

(ii) 	on the specifications, drawings and other data which are to acCOMPANY bid requests, purchase orders, CONTRACTs and like commitments;

(iii) 	on the manufacturers, fabricators, suppliers and sub-CONTRACTORs selected for award;

(iv)	on matters in the bid requests, proposals, bids or tenders, purchase orders, subCONTRACTs and like commitments  relating to warranties, guarantees, spare parts, alternatives sought and offered, title transfer, and information and/or data relating to installation, start-up, operating and maintenance procedures and services.

(v) 	on the specifications, drawings and other documents (excluding pricing) submitted to CONTRACTOR by manufacturers, fabricators, suppliers and  subCONTRACTORs;

(vi)	on CONTRACTOR's plans to accept as complete, or to terminate purchase orders, subCONTRACTs and like commitments.

(vii) on the contents of purchase orders, subCONTRACTs and like commitments (except as to pricing).

CONTRACTOR SHALL submit complete Purchase orders and material requisitions to COMPANY for approval.

The complete Purchase order SHALL contain as a minimum the following documents:

- 	Scope of supply/quantities and name of suppliers.

- 	Design, Fabrication, Inspection and Certification requirements.

- 	Delivery time, preparation for shipment, preservation and marking.

- 	General Specifications and construction practices;

- 	Applicable codes and regulations.

- 	Drawings and datasheets.

- 	Complete bid including clarifications and qualifications and excluding prices from the successful supplier.

-	SPIR Form

CONTRACTOR SHALL give COMPANY and its Representative/Consultant opportunity for such approval and comments before taking irreversible action or making significant monetary commitment with respect to such purchase orders, subCONTRACTs or likes commitments.

Accordingly, CONTRACTOR SHALL present such documents particularly including the specification, drawings and other documents detailing manufacturer's, fabricator's, supplier's or sub-CONTRACTOR's proposal as submitted to and accepted by CONTRACTOR, to COMPANY's Representative in a timely manner.

The CONTRACTOR SHALL give the COMPANY time for approval and comment, and SHALL respond to COMPANY's comments, if any, before taking further action with respect thereto.

Neither COMPANY’s review, and/or absence of comment SHALL relieve CONTRACTOR of responsibility for adherence to contractual specifications.

During procurement, CONTRACTOR SHALL obtain as appropriate for each item all necessary installation, operation, maintenance and repair information and instructions, other like data and documents as more precisely described elsewhere in this CONTRACT or as required by COMPANY's Representative, for all material and equipment to be incorporated into the WORK. Such data and information SHALL be furnished to COMPANY's Representative as received, but not later than thirty (30) days prior to the planned date of issue of the "Certificate of Provisional Acceptance (PAC) of the WORK".

CONTRACTOR's procurement of all material, equipment and consumable items to be imported into the Syrian Arab Republic SHALL be made in the name of COMPANY.

The following address SHALL be used by the CONTRACTOR for the imported materials shipping documents:

-	Markings to appear on all shipments destined for COMPANY ARABGAS PIPE LINE PROJECT PHASE /II/  should be stencilled with paint as follow:

SYRIAN GAS COMPANY-SYRIA

ARAB GAS PIPELINE PROJECT - PHASE  II.

Destination Code: xx-x-xx

Purchase Order Number:

Gross Weight:

Dimension:

Pkg. ----- of-------

Destination codes will be comprised of:

Plant/Unit, followed by identifier numbers (as per tag, drawing or bill of materials numbers).

Destination codes for spare parts will comprise of:

The above identifier numbers followed by “SPARES”.

The equipment “tag number” as it appears in the Purchase Order description, SHALL be imprinted on a noncorrosive metal tag and firmly attached to the item in such a manner that it will not easily be born off.

Any materials catogorized as dangerous goods are to be so identified.

Fragile or breakable materials to be clearly identified.

Center of gravity clearly shown with point marking.

COMPANY SHALL reserve the right to disapprove CONTRACTOR's procurement of any material, equipment and consumable items, if they do not meet the requirements and specifications of the CONTRACT.

All Purchase orders SHALL have a statement clearly stating that the “warranty is transferable to the COMPANY name”.

3.2 	Delivery and Transport

Delivery and Transport SHALL include, but not be limited to, the following activities for CONTRACTOR furnished items, including spares:

(i) 	all transport from vendors/manufacturers to ship, aircraft or alternative means of 	transport;

(ii) 	all transport of material/equipment from country of  origin to Syria (either sea, land or 	air);

(iii)	all delivery, logistical and customs clearance  functions in country of origin, as well as in Syria;

(iv) 	all transport in Syria to the Site;

(v) 	all related insurance;

(vi) 	all preservation and storage, en-route and at site.

(vii)	all material will be accompanied by the relevant documentation, e.g. material certificate.

(viii) all package material SHALL be property of COMPANY.

Delivery and Transport SHALL also include, for COMPANY furnished items, if any, and for CONTRACTOR furnished items.

4.0 	CONSTRUCTION

Construction SHALL include, but not be limited to:

(i) 	All functions associated with safe working at the Site, and compliance with Exhibits, with emphases of the following aspects:

-  journey management

-  safety meeting

-  toolbox meeting

-  emergency procedures.

-  notice board.

(ii) 	the preparation of foundations, road crossings, pipe  trenches and reinstatement to original condition.

(iii)	the assembly, erection and installation of materials and equipment including all elements, components,  interconnecting systems, access ways and platforms;

(iv) 	connection to the existing facilities including: piping, instrumentation, electrical and control systems, so as to avoid shutdown time required for the tie-ins.

(v) 	all isolating, unbolting, cleaning, de-oiling, de-gassing and safe evacuation of process media from existing facilities, upon depressurising of the facilities and prior to commencement of tie-in work by CONTRACTOR.

(vi) 	the performance of all inspections and testing.

(vii)	the provision of on-Site vendor representatives.

(viii) the provision for COMPANY's use of on-Site office space and related furnishings, equipment and services;

(ix) 	Clean-up and removal of construction equipment and materials from the construction/installation locations.

(x) 	CONTRACTOR SHALL include all functions associated with safe working at any site close to operating facilities, and comply with COMPANY's safety  regulations.

(xi) 	CONTRACTOR will submit to COMPANY, four (4) weeks prior to any construction activities, a QA/QC plan to cover all construction, pre-commissioning and testing activities.

The QA/QC will be used from the start of construction to the completion of the pre-commissioning activities and will be signed off by both CONTRACTOR and COMPANY at every stage.

The QA/QC plan is subject to COMPANY approval.

(xii)	The preparation of work procedures, submitted to COMPANY representative(s) for approval. These procedures SHALL be submitted to COMPANY at least two weeks prior to start of the works.

(xiii)Preparation of spade list and golden weld list and submitted to COMPANY for review/approval.

(xiv)Provision of all necessary safety and construction equipment, such as gas detectors and scaffolding.

(xv)	Adhere to the CONTRACT changes procedures; report any changes/deviations from the “Frozen” design and CONTRACT specification formally to COMPANY for approval.

(xvi)Use a marker and colour code system for piping, pipelines and flowlines and identification system for the equipment skids. The colour code and identification systems SHALL be subject to COMPANY approval.

All WORK performed within COMPANY operating areas must be done under COMPANY’s Permit to Work (PTW) system. This must be reflected in procedures submitted by CONTRACTOR. In case WORK is to be carried out in operating areas of third parties, the WORK is to be carried out under the third party Permit to Work System.

Where appropriate and agreed by COMPANY, CONTRACTOR SHALL remove a part of the existing fence and fence the dedicated area for the to-be-installed facilities as shown on the relevant plot plan. The temporary fencing SHALL be 30 meters away from existing facilities. If these criteria cannot be met, the COMPANY Permit to Work System SHALL be adopted by CONTRACTOR.

CONTRACTOR SHALL take full account of lead times for safety discussions and processing of PTW in his implementation schedule.

Construction SHALL also include all related actions necessary to render the entire facility in a complete and proper state acceptable to COMPANY.

5.0 	PRECOMMISSIONING, COMMISSIONING AND ACCEPTANCE TESTING

During this stage of the PROJECT, the plant/facility may not be at full design throughput and consequently, the plant may be subjected to abnormal operation during the testing of an item/system. The abnormality must however not exceed the design limits of the facility.

5.1 	Precommissioning.

Precommissioning SHALL include, all requirements as laid down below, but not be limited to, all activities associated with bringing the constructed facilities into such a state as will permit introduction of process media and commissioning of the facilities.

Precommissioning will take place during the final stages of the construction phase, but can only commence when CONTRACTOR has obtained COMPANY’s approval on CONTRACTOR's pre- commissioning schedule and manual.

Pre-commissioning SHALL include, but not be limited to:

(i) 	the successful conduct of hydrostatic, mechanical and  electrical tests.

(ii) 	the loop testing, calibration and setting of control and monitoring devices.

(iii) 	the checking of the alignment, rotation and tightness of all elements of the facilities.

(iv) 	the flushing, cleaning and purging of the completed facilities to permit operation without damaging or failing mechanical equipment or adulterating the product.

(v) 	the provision of on-Site vendor representatives.

(vi) 	physical inspection of items, plant or equipment to ensure that all is completed and has been installed in accordance with Drawings and Specifications.

(vii)	checking and testing defined above, but including energising and the coupling of the various systems for an overall functional check prior to full on-line  plant commissioning.

(viii) rotating equipment alignments are checked and prime movers are run for at least four (4) hours uncoupled.

(ix) 	all instruments, control panels, electrical and mechanical equipment, including auxiliaries and  control systems, are serviced, adjusted, loop-tested,  calibrated and set for normal operation.

(x)	all function tests identified by COMPANY.

(xi)	purging the new facilities with N2 and ensure the O2 ratio is within the acceptable level as per COMPANY specification.

CONTRACTOR will be responsible for and perform the pre-commissioning works, which are to be witnessed and signed off by COMPANY.

CONTRACTOR will arrange for the documents required to form a complete record of all testing and running procedures and results.

Prior to commissioning all punchlist items designated  "essential to be completed before introduction of process media" SHALL be completed to the satisfaction of COMPANY.

5.2 	Introduction of Process Media

Seven (7) days before completion of all construction pre-commissioning and safety system verifications, as mentioned elsewhere in this Schedule, of the total of all facilities to be supplied as required per CONTRACT scope of work, CONTRACTOR SHALL issue to COMPANY representative a notice stating when the facility will be completed and ready for the introduction of process media and ready to maintain a sustained flow of process media thereafter.

COMPANY SHALL then carry out a pre-start-up audit on the facilities installed and constructed and SHALL review and approve or comment on CONTRACTOR's pre-commissioning and safety system verifications.

If these activities have been completed to COMPANY representative's satisfaction and CONTRACTOR has obtained COMPANY representative's approval on

CONTRACTOR’s commissioning schedule and commissioning manual, COMPANY representative will issue a notice, signed by the COMPANY, that the facility is suitable for the introduction of process media.

Being in receipt of the signed notice does not relieve CONTRACTOR of the continued responsibility to rectify malfunctioning of equipment and related systems during plant start-up.

5.3  	Commissioning.

5.3.1 General

CONTRACTOR SHALL carry out all commissioning activities, in accordance with the commissioning plan.

It is the responsibility of CONTRACTOR to ensure that in the early stages of construction a commissioning plan/schedule is prepared, which will require the approval of COMPANY.

Commissioning SHALL include all activities associated with start-up and initial operation of the facilities so as to permit CONTRACTOR to conduct performance and acceptance tests of the new facilities.

CONTRACTOR SHALL take into account that commissioning of plant after the introduction of process media or at any other time so stipulated is subject to COMPANY's Permit to WORK system.

Commissioning SHALL include, but not be limited to, all requirements as laid down below:

- Introduction of hydrocarbon into the newly constructed pipeline and facilities.

- Successful testing of control and shutdown systems associated with the existing and newly constructed pipeline and facility(s);

- The successful operation of SDV and BVS valves, running of scraper and metering equipment, associated with the constructed PROJECT.

- Performing of Site Acceptance Test (SAT) of control/monitoring system.

- Testing and, if appropriate, recalibration of control loops and instruments under normal operating conditions;

- Availability of on-site Vendors/Manufacturer representative(s);

- The PROJECT is proven to be capable to sustain the design flow conditions or flow conditions as near as practical to the design conditions, which can be achieved depending on availability of hydrocarbons, (with prior agreement of COMPANY) for an uninterrupted period of 24 hours minimum; and

- Successful execution of 72-hour acceptance tests in accordance with RFQ specification and design conditions and CONTRACTOR’s procedures for acceptance and performance testing which is approved by COMPANY.

Before starting the 24-hr test CONTRACTOR will have completed, as a minimum, the following:

-  installation of all equipment

-  perform the all tests required

-  all test packs signed off

-  all commissioning spares  available at site.

Relevent documentation SHALL be presented to COMPANY representative(s) for review.

Commissioning SHALL be executed by the CONTRACTOR with the full cognisance and agreement of the COMPANY. CONTRACTOR is required to attend daily commissioning meetings at which COMPANY representatives will require detailed briefings on which systems are to be commissioned.

CONTRACTOR will remain responsible for the correct and safe operation of the newly installed facilities during commissioning.

5.3.2 Commissioning.

The COMPANY will audit the pre-commissioning carried out by CONTRACTOR.  The requirements for test equipment and materials SHALL be defined in the commissioning procedures and SHALL be provided by CONTRACTOR as part of this CONTRACT.

Commissioning SHALL be carried out on a systems basis, starting with the utilities to be followed by the production systems.

During commissioning CONTRACTOR will make available experienced operators (for day and night shift).

The CV’s of CONTRACTOR commissioning Engineer SHALL be submitted for COMPANY approval.

5.3.3 Ready for Acceptance Testing.

Seven (7) days before completion of all commissioning activities as mentioned elsewhere in this Schedule of the total of the facilities to be supplied as required per the CONTRACT scope of work, CONTRACTOR SHALL issue to COMPANY Representative a notice stating when the facility will be ready for acceptance testing.

COMPANY SHALL then carry out a review of the facilities commissioned and approve or comment on CONTRACTOR's commissioning activities.

Upon stabilisation of the facilities and on completion of any work required by COMPANY to enable approval to be given to CONTRACTOR to request to start acceptance testing, COMPANY will issue a notice that the facilities are ready for acceptance testing provided, in addition, that CONTRACTOR has issued the Acceptance Testing Manual and has obtained COMPANY approval on CONTRACTOR's acceptance test manual.

Following stabilisation of the plant under operating conditions, the CONTRACTOR under the guidance of COMPANY and as set out in paragraph "Acceptance Tests" SHALL perform Acceptance Testing. The Acceptance Test will subject each item/system to its design performance.

5.3.4 Acceptance Tests.

CONTRACTOR SHALL subject the facilities to appropriate acceptance tests, in which all equipment and systems will be operated at design conditions or as near thereto as practicable. The purpose of such tests is to ascertain whether CONTRACTOR has fulfilled his obligations under this CONTRACT.

CONTRACTOR SHALL submit a proposal, for COMPANY's approval, for a list of process parameters and acceptance criteria that he intends to monitor during the uninterrupted 72-hr acceptance test to prove that the design parameters are achieved.

Before starting the 72 hr test, CONTRACTOR will demonstrate, with appropriate document that:

-  No major outstanding (no major item in the punch list) works/equipment missing.

-  The CONTRACTOR Operations team is prepared and mobilised on site.

If the acceptance tests reveal any defects, defaults or deficiencies in CONTRACTOR's performance of this CONTRACT, COMPANY will give prompt notice to CONTRACTOR setting forth the particulars, whereupon CONTRACTOR, at its cost and expense, SHALL promptly correct such defects, defaults or deficiencies as prescribed in COMPANY's notice.

Following CONTRACTOR’s corrections, COMPANY will require those portions of the facilities that have been corrected to be submitted to further Acceptance Tests as originally conducted.

CONTRACTOR remains responsible for the correct and safe operation of the facilities during acceptance testing and SHALL maintain COMPANY permit to work system for all work carried out during this period.

CONTRACTOR SHALL fully cooperate with COMPANY during the implementation of the Acceptance Tests, to safeguard the operation of the new and existing production installations.

5.3.5 Issue of "Certificate of Provisional Acceptance of the WORK".

Upon the successful completion of the uninterrupted 72 hrs acceptance testing of the facilities, CONTRACTOR will issue a notice to that extent, together with a summary of the outstanding work, which has not been performed at that date and included in punch list.

If the COMPANY accepts the results of the acceptance testing and acknowledges that no main work is outstanding and punch list is clear, then COMPANY will issue a "Certificate of Provisional 	Acceptance of the WORK". Upon granting the "Certificate of Provisional Acceptance of the WORK", the outstanding work by CONTRACTOR SHALL be limited to:

- 	site clean-up;

- 	demobilisation of CONTRACTOR's facilities, equipment and personnel;

- 	items considered minor by COMPANY only, which do not hinder the operations or maintenance.

The outstanding work by CONTRACTOR SHALL be included in a punch list. Each item in the list SHALL have an agreed completion date, the list SHALL be signed by both the COMPANY and the CONTRACTOR.

5.3.6 Hand-over

At the date of issue of the "Certificate of Provisional Acceptance of the work", the facilities are handed over by CONTRACTOR to COMPANY.

COMPANY will take over operation and maintenance of the facilities under the conditions of CONTRACT documentations.

- WARRANTY.

As per “Contract Standards Terms and Conditions (Draft Contract), Exhibit-E”

8.0 	ISSUE OF "CERTIFICATE OF FINAL ACCEPTANCE OF THE WORK".

Thirty (30) days before the termination of the warranty period, CONTRACTOR SHALL notify COMPANY of the forthcoming expiry of the warranty period. After receiving CONTRACTOR's notice and provided that there are no outstanding warranty claims, COMPANY will issue the "Certificate of Final Acceptance of the work" as per the CONTRACT terms and conditions.

In case one or more warranty claims are still outstanding at the termination of the warranty period, the Performance Bond will remain in force until these warranty claims are resolved to COMPANY's satisfaction.

9.0 	SPARE PARTS, SPECIAL TOOLS, TESTING EQUIPMENT & OPERATING SUPPLIES

Spare Parts, Special Tools, Testing Equipment and Operating Supplies SHALL be procured and delivered by CONTRACTOR to COMPANY at Site or to the COMPANY field warehouse as detailed below.

9.1 	Spare Parts

9.1.1 General

Spare parts furnished by the CONTRACTOR hereunder SHALL be manufactured using the same drawings, specifications, processes, tolerances and materials as the parts used in the original equipment which they are intended to replace.

Such parts SHALL be fully interchangeable with the original without modification to the parts or equipment and SHALL be properly identified and packed for long-term storage.

9.1.2 Start Up and Commissioning Spare Parts.

CONTRACTOR SHALL supply and transport to site at his own cost all spare parts necessary for the Start-up and Commissioning, and Initial Operation until the issue of the Certificate of Provisional Acceptance of the WORK.

Within two months of placing the order for the main equipment CONTRACTOR SHALL give to the COMPANY Representative a list of range and quantities of parts he intends to deliver to site and SHALL maintain at site until Issue of the Certificate of Provisional Acceptance maintain at site a register showing receipts issues and current stock.

The stocks and the register SHALL be available for inspection by the COMPANY’s Representative at his request. The register SHALL be handed to the COMPANY's Representative at Issue of the Certificate of Provisional Acceptance of the WORK.

At no cost to COMPANY and prior to the date of issue of the Provisional Acceptance Certificate of the WORK, all the unused remaining Start up and Commissioning spare parts SHALL be delivered to COMPANY’s field warehouse.  Used parts, which are still servicable, SHALL be delivered to the COMPANY Representative at the PROJECT site.

9.1.3 Normal Operation.

CONTRACTOR SHALL provide the spare parts necessary to support two years continuous operation and as required by COMPANY in the list, of the facilities to be constructed under this CONTRACT. All costs of the procurement, transportation and delivery SHALL be part of the CONTRACT lump sum.

CONTRACTOR SHALL deliver the spare parts approved by the COMPANY under this Article to the COMPANY's, Rayan warehouse prior to the issuing of Provisional Acceptance Certificate of the WORK.

Delivery shall be a condition of Issue of the Certificate of Provisional Acceptance of the WORK.

CONTRACTOR's furnishing of spare parts pursuant to this Article SHALL not relieve CONTRACTOR of his obligations under the Exhibit 'K' article titled "Warranty".

9.1.4 Spare Parts List and Interchangeability Record (SPIR) Forms.

CONTRACTOR SHALL provide spare parts recommendations on Spare Parts List and Interchangeability Record forms (SPIR) compiled by the manufacturer of each item of equipment. The P.O list will be used to ensure that all equipment are covered by the SPIR. In the monthly report the SPIR status list SHALL be included.

Equipment SHALL be defined as any item in plant, machinery, product transfer or treatment system, electrical power supply system control system of any type, communication system, building or building services, including power and water supply, air-conditioning and the like, which has wearing or deteriorating parts designed to be replaced during the item's life.

Equipment SHALL also include any special test equipment to be supplied under "Special Tools and Testing Equipment".

By the milestone defined at the CONTRACT as "Purchase Orders issued for long lead items" the CONTRACTOR SHALL give to COMPANY Representative a list of the SPIRs he intends to provide, showing each SPIR number, the Equipment Manufacturer and equipment type.

CONTRACTOR SHALL submit the completed SPIRs to the COMPANY at the COMPANY's Office in such date to allow a sufficient time for review, approval and addition of any further parts required by the COMPANY, but in any case not later than two months after placing the order for the main equipment.

The submission to COMPANY's representative SHALL include the originals and two fully legible copies of each SPIR and three copies of supporting technical information obtained from manufacturer's, including illustrated parts lists, brochures and where available recommended maintenance schedules.

Compilation of SPIRs SHALL be as per Appendix "4" and CONTRACTOR SHALL arrange that all equipment enquiries include advice to the manufacturer, that he will be required to complete SPIR forms in accordance with that Annex.

Manufacturer's listings SHALL indicate the range of parts likely to be used during the life of the equipment and parts, which should be held as insurance.

It SHALL also show for two-year parts and insurance items the recommended quantities. The list SHALL acknowledge the arduous desert-operating environment.

9.1.5 Ordering for Normal Operation.

COMPANY SHALL review each SPIR and place an order on CONTRACTOR for required parts. Normally this will be by letter covering a suitably amended SPIR.  A dedicated purchase order number SHALL be used for each SPIR.

9.2 	Special Tools and Testing Equipment.

CONTRACTOR SHALL supply with, and as part of, the equipment all special tools and testing equipment which are of a type not normally used by craftsmen and which are required to test, calibrate, service and maintain the various items of equipment included in the WORK.

The nature and quantities of such special tools and testing equipment SHALL be as recommended by the manufacturers of the various equipment items, but subject to COMPANY Representative's approval.

CONTRACTOR SHALL obtain from each equipment manufacturer specific advice on the range and quantity of special tools and test equipment needed to support his product and SHALL submit to COMPANY representative for approval a list with appropriate supporting technical information.

CONTRACTOR SHALL ensure that the COMPANY’s approved special tools and testing equipment are handed to COMPANY Representative at the Site prior to Provisional Acceptance of the WORK. The Issue of the Certificate of Provisional Acceptance of the WORK SHALL be conditional on that delivery.

Subject to COMPANY's Representative's approval, CONTRACTOR may use the special tools and testing equipment obtained under the foregoing provisions in the installation and testing of the applicable items of material and equipment.  Any other tools and equipment required by CONTRACTOR to perform the WORK should be furnished by CONTRACTOR without cost to COMPANY.

  - Operating Supplies.

Definition

Operating Supplies SHALL be defined as those consumable items other than equipment spare parts required to keep the process medium in the designed condition at maximum designed capacity; and keep the equipment, plant and any additional items specified in the WORK operating in the designed manner.  Equipment includes all quality and quantity measuring instruments and peripherals whether fixed or portable supporting the facility process.

Operating Supplies SHALL include such items required by new facilities or an addition or modification to existing facilities. They SHALL also include new items needed in existing facilities as a result of the CONTRACTed WORK.

Operating Supplies SHALL include but not be limited to the items listed in Appendix "8" Part 1.

General

Operating Supplies, which are hardware, SHALL be manufactured using the same specifications, drawings, processes, tolerances and materials as the original they are intended to replace.

They SHALL be fully interchangeable with the original without modification to either.  As far as practical, Operating Supplies, SHALL be the same as COMPANY already uses.

Delivery SHALL, be in accordance with Appendix "8" Part 4.

Start-up, Commissioning and Initial Operation.

CONTRACTOR SHALL supply all "Operating Supplies" and other consumables necessary for Start-up, Commissioning and Initial Operation until the Issue of the Certificate of Provisional Acceptance of the WORK.

Any unused quantities SHALL be handed over to COMPANY in addition to operating supplies provided for Normal Operation. Unused quantities, which are still securely and properly packed, SHALL be delivered to COMPANY's Rayan warehouse.

The remainder SHALL be delivered to the PROJECT site.

Normal Operation

CONTRACTOR SHALL provide and deliver to COMPANY Rayan warehouse, chemicals and other operating supplies sufficient for two (2) years normal continuous operation at maximum design capacity.

Delivery SHALL be prior to Commissioning and a condition of Issue of the Certificate of Provisional Acceptance of the WORK.

Preliminary List

Within one month after placement of order for the main equipment CONTRACTOR SHALL submit to the COMPANY Representative a Preliminary List outlining the scope and nature of operating supplies he proposes.

The list SHALL include information listed at Appendix "8" Part 2.

Detailed List

Within three months after placing the order for the main equipment CONTRACTOR SHALL submit to COMPANY Representative for approval a Detailed List of the operating supplies he proposes to deliver showing for each the quantity for Start-up, Commissioning and Initial Operation and the quantity for the first period of Normal Operation as defined above and first filling.

The submission SHALL include copies of relevant information received from manufactures and vendors and for each item the information listed at Appendix "8"       Part 3.

Site Stock Register.

Until issue of the Certificate of Provisional Acceptance the CONTRACTOR SHALL keep at site a register of stocks of operating supplies held for start-up, commissioning and initial operation.

It SHALL show receipts, issues and current stock.

The register and stocks SHALL be available for inspection by COMPANY's representative at his request.

The register SHALL be handed to COMPANY's Representative prior the Issue of the Certificate of Provisional Acceptance of the WORK.

10.0	Deleted.

11.0 	CONTRACTOR’S ON-SITE FACILITIES AND SERVICES

CONTRACTOR SHALL inform COMPANY representative when the CONTRACTOR's on-site facilities and the facilities to be provided for COMPANY is considered complete.

11.1 Security

CONTRACTOR SHALL furnish all personnel, equipment and supplies required to provide a continuous on-site security service.

The purpose of such security service SHALL be to permit entry to the construction sites of only those persons authorised by COMPANY, to assist in the prevention of pilferage of material items, to maintain orderly conduct on the Site and to attend to other scheduled and unscheduled security situations.

CONTRACTOR SHALL follow the requirements of the laws of the Syrian Arab Republic in the performance of such security services.

11.2 Sanitation

CONTRACTOR SHALL furnish all labour, equipment and supplies to provide, service and maintain adequate sanitary and decent on-site sanitation facilities.

This SHALL include hot shower facilities and running water within the toilets. Both toilet and shower facilities SHALL be cleaned daily by a dedicated cleaner.

Such facilities SHALL be provided adjacent to each location where WORK is being performed.

CONTRACTOR SHALL also perform daily clean up of the Site so as to maintain a tidy and safe work environment which is vermin and vector free.

11.3 Project Signboards

On request of COMPANY, CONTRACTOR SHALL provide and erect a PROJECT signboard at each principal area at the Site where WORK is performed.

The cost of these signboards is deemed to be included in the CONTRACT Price.

Such signboards SHALL show both in the Arabic and English language the PROJECT title, the CONTRACT title and COMPANY's and CONTRACTOR's names and logos.

Such signboards SHALL be subject to COMPANY’s Representative approval with respect to size, construction, wording, calligraphy, support, location and numbers.

11.4 Vendor Representatives

CONTRACTOR SHALL, with respect to complex and/or sophisticated items or material and equipment furnished by CONTRACTOR pursuant to Exhibit “J”, provide on-site services of vendor representative(s).

Such vendor representatives SHALL be an employee of or accredited to the manufacturer or vendor of the applicable material and equipment and he SHALL be knowledgeable in the technical aspects of the material and equipment.

Vendor representatives SHALL assist and advise CONTRACTOR and/or COMPANY (as the case may be) in the safe, proper and expeditious receipt, storage, handling, installation, testing, precommissioning, calibration and start-up of the applicable material and equipment and of the PROJECT as a whole.

Such vendor representative SHALL be available on Site at such times as are required on technical grounds and at such times as are necessary for CONTRACTOR to adhere to applicable contractual schedules.

All CONTRACTOR's costs incurred in the compliance with this article SHALL be deemed to be included in the CONTRACT Price and such costs SHALL not be the subject of separate payment by COMPANY.

11.5 	Facilities and Services for COMPANY's Representative on-Site

CONTRACTOR SHALL provide for COMPANY the on-site facilities, amenities and services as stipulated in this section.

All the on-site facilities, amenities and services SHALL be available from the start of construction until two weeks after the issue of the Certificate of Provisional Acceptance of the WORK.

The provision of the facilities, amenities and services SHALL be subject to COMPANY Representative prior and/or ongoing review and approval.

11.5.1 	Office, Furnishings, Equipment, Assistance and Services

CONTRACTOR SHALL provide ateach  construction base camp, as a minimum four offices to serve as four (4) individual heated/airconditioned offices.

All offices SHALL be provided with all normal office furnishings and equipment, including but not necessarily limited to, desks, tables, chairs, telephone, filing cabinets, fridge, white board and drawing holder racks As the following but not limited to :.

    - 4 (four) offices with minimum area of 80(eighty) square meter (totally)  in the main camp for each PART of PROJECT                                         these offices shall be furnished as minimum  with the following as totally  for each main camp :

-four (4) window type (cold / hot) air conditioners

-ten (10) wooden table

-twenty (20) wooden chair

-Six (6) file cabinet

-four (4) latest version computer with all accessories (from the contract commencement date) and equipped with CD writers

-One (1) latest version lap-top

-One (1) copy machine (A3/A4)

-One (1) fax machine

-One (1) telephone

-Two (2) laser jet printer

-One (1) color printer

In addition to daily offices requirement and daily janitorial services

    - 2(two) offices along pipeline rout for each PART of the PROJECT

Each office shall be furnished with the following as minimum:

-One (1) wooden table

-Three (3) wooden chair

-One (1) file cabinet

In addition to daily offices requirement and daily janitorial services

    - Daily accommodation and catering for15(fifteen) personnel for each main camp

The company shall reject such furniture, accommodation and catering if did not meet the company satisfaction and acceptance

The cost of such services including telecommunication shall be deemed to be included in the Contract Price and such costs shall not be the subject of separate payment by COMPANY.

CONTRACTOR SHALL also provide all required stationery and office supplies and daily janitorial service.

12.0 	SUBCONTRACTING

In addition to the CONTRACT requirement stipulated in Exhibits, CONTRACTOR SHALL not employ any subCONTRACTOR before having a written COMPANY approval.

PART B - PROJECT ADMINISTRATION

1.0	CONTRACTOR DOCUMENTATION REQUIREMENTS

This Specification defines the administration and documentation requirements for the execution of the CONTRACT. Documentation SHALL include, but not be limited to, CONTRACTOR's submittal to COMPANY of all:

(i)	Schedules

(ii) 	Reports

(iii) 	Information (as defined in paragraph titled  "CONTRACTOR Prepared Information")

(iv) 	All other submissions required pursuant to all Exhibits.

(v) 	Pre-commissioning and commissioning documentation as specified elsewhere in this CONTRACT

(vi) 	Manufacturing data books

(vii) 	Operations Manuals

(viii) 	Maintenance manuals and HSE manual

(ix) 	As-builts

2.0	CONTRACTOR SCHEDULING REQUIREMENTS

In preparing any Schedules, CONTRACTOR should be aware that importation, whether temporary or permanent, of certain equipment may be subject to extensive and time consuming clearance by Syrian customs. This includes computers (including EMCS, and ESD systems), telecoms equipment, software and handheld radios for on site communications.  CONTRACTOR will furthermore take into account any export permit required in his scheduling activities.

2.1 	SCHEDULE FORMAT

2.1.1 Precedence Network

The Precedence Network SHALL show the detailed activities and logic sequence of activities as per appropriate level needed for the orderly performance and completion of every separable part of the WORK in order to meet the milestones stipulated for each major event as shown on the schedule included in Exhibit “D”.

CONTRACTOR SHALL be responsible for utilising all information as required to establish the availability of all materials and equipment, including those provided by COMPANY to support scheduled activities, as well as assessing the activity durations, labour resource availability etc.

CONTRACTOR SHALL monitor status reports and identify potential schedule problems to COMPANY.

Such problem identification SHALL be accomplished sufficiently far in advance to minimise the impact of the problem and to allow for alternative courses of action to be planned and implemented.

2.1.2 	Barchart

CONTRACTOR SHALL present his schedule for the performance of the WORK in the format of a barchart with weekly and monthly time intervals.

The barchart SHALL be based on the logical sequence of activities from the precedence network and SHALL show the milestones stipulated for each major event as shown on the schedule included in Exhibit “D”, and SHALL show the base line dates as agreed by COMPANY.

2.1.3 	Manpower Histogram

The schedule SHALL show the aggregate of resources for the performance of the WORK for each weekly period.

Manpower SHALL be presented in the form of a manpower histogram identifying individual disciplines so as to satisfy COMPANY that sufficient skills and numbers are made available to complete the Work within COMPANY Plan Dates.

2.2 	CONTRACTOR's Scheduling Commitments.

During the course of the CONTRACT, CONTRACTOR SHALL prepare and submit monthly for the review and approval of COMPANY detailed schedules as required by this article.

The schedules submitted by CONTRACTOR as required hereunder SHALL exhibit mutual interrelationship and consistency from one schedule to another.

The schedules prepared by CONTRACTOR and submitted for COMPANY’s review will be subject to COMPANY's evaluation and approval, and will be subject to discussions between COMPANY and CONTRACTOR. Such discussions will involve a review of the current status of CONTRACTOR's progress on each scheduled activity and this CONTRACT as a whole, CONTRACTOR's plans for future WORK and CONTRACTOR's proposals, if required, to correct any areas where CONTRACTOR's progress of WORK has fallen, or is likely to fall, behind schedule.

2.2.1 	Contract Implementation Schedule

CONTRACTOR SHALL plan and schedule the WORK in his Implementation Schedule to ensure achievement of the COMPANY Plan Dates as detailed in Exhibits “D”.

CONTRACTOR SHALL acknowledge that COMPANY Plan SHALL take precedence over CONTRACTOR’s Implementation Schedule and SHALL constitute the dates upon which PAC achievement is assessed.

The Implementation Schedule SHALL be submitted for COMPANY review.

The Implementation Schedule SHALL consist of a detailed Precedence Network and a summary Level 1 Barchart, supported by consistent detailed Level 2 Barcharts and identifying the logistics involved in accomplishing the CONTRACT Hardware and Documentation Deliverables within the assigned COMPANY Plan dates. Critical Path activities and allocated float SHALL be identified.

The Schedule SHALL identify target completion dates for all CONTRACT Hardware and Documentation Deliverables. CONTRACTOR should assign float at his sole discretion to ensure that slippage does not impact on COMPANY Plan dates.

Level 1 Management Summary SHALL show COMPANY Plan dates as discrete milestones from CONTRACTOR’s Implementation Schedule data.

Level 2 Overall Schedule SHALL identify individual phases of the PROJECT with major activities and the timing of key Interface Control activities, featuring in CONTRACTOR’s Interface Control management system and Report.

Level 2 SHALL include and clearly indicate CONTRACTOR’s allowances for the quoted delivery times of Long Lead items of equipment. Critical equipment items SHALL be identified.

Level 3 Detailed Schedules SHALL be submitted showing all detailed activities and resources within each phase and for any activity identified as critical activities, to highlight which specific activities are of critical concern. The degree of criticality and allocation of float SHALL be identified.

This level of planning SHALL be provided for all concurrent operations and shutdown activities as a key ingredient for Concurrent Operations Planning in conjunction with COMPANY Representatives, when a shutdown of process equipment is essential, and to ensure the work is undertaken in the shortest possible timespan.

Wherein critical path activities are identified or developed during the CONTRACT then Schedules SHALL be submitted to COMPANY, complete with an explanatory written narrative detailing the measures by which CONTRACTOR intends to safeguard any perceived risks to critical path activities from causing delay to COMPANY Plan dates.

CONTRACTOR SHALL be obliged to state and demonstrate the criticality of any potential delay in COMPANY response prior to issuance of a CONTRACT Deliverable for COMPANY further action such that COMPANY Representatives are directly aware of the consequences of any potential delay at time of its receipt.

COMPANY SHALL retain the right to require CONTRACTOR to submit any additional information necessary to permit the COMPANY action to be completed.

CONTRACTOR SHALL, on a continuous basis, monitor the status of each activity shown on the schedule and SHALL, at monthly intervals together with the Monthly Report, update and resubmit the CONTRACT Implementation Schedule so that actual progress is reflected and SHALL indicate activities or actions proposed by CONTRACTOR to overcome any schedule shortfall that may have occurred during the periods covered by previous submissions.

2.2.2 	Site Construction Schedule

At least thirty (30) calendar days prior to CONTRACTOR's commencement of Construction work CONTRACTOR SHALL prepare and submit for COMPANY's review and approval, CONTRACTOR's detailed schedule for the performance of the site construction WORK.

The schedule SHALL be based on the CONTRACT Implementation Schedule and SHALL identify all activities in the electrical, instrumentation, civil, mechanical and structural disciplines as well as precommissioning and testing necessary for the performance of the WORK.

2.3	Left blank

2.4 	Testing Schedules

Sixty (60) calendar days prior to CONTRACTOR's performance of any test (including Factory Acceptance Tests (FAT)), CONTRACTOR SHALL prepare and submit for COMPANY’s review and approval, two schedules:

1. 	as part of CONTRACTOR's procurement efforts; and

2. 	of materials and/or equipment installed and/or modified by  CONTRACTOR on site.

2.4.1 	Test Schedule for CONTRACTOR Procured Equipment/Materials

The schedule SHALL be based on the CONTRACT Implementation Schedule and SHALL identify all equipment and materials to be subject to (performance/acceptance) tests, the timetable for conducting same and procedures to be followed by CONTRACTOR and vendor/manufacturer.

2.4.2 	Test Schedule for On-site Pre-Commissioning

The schedule SHALL be based on the CONTRACT Implementation Schedule and SHALL identify all systems and sub-systems to be subject to pre-commissioning activities and tests, the timetable for conducting same and SHALL list major items of  (testing) equipment and vendor representatives to be utilised.

CONTRACTOR SHALL notify COMPANY’s Representative immediately prior to commencement of the test(s). Testing activities SHALL be witnessed and co-signed by CONTRACTOR’s and COMPANY's Representatives.

2.5 	Commissioning Schedule

Together with the Implementation Schedule, CONTRACTOR SHALL submit a Level 1 commissioning Schedule, identifying system sequence and critical equipment.

Prior to CONTRACTOR's performance of any commissioning, CONTRACTOR SHALL prepare and submit for COMPANY's review and approval CONTRACTOR's schedule for the commissioning, including the sequence of system commissioning, which is to be carried out on the facilities installed and/or modified by CONTRACTOR.

The schedule SHALL be based on the CONTRACT Implementation Schedule and SHALL identify all systems and subsystems to be subject to commissioning activities and (performance/acceptance) tests, the time table for conducting same and SHALL list major items of equipment and vendor representative services to be utilised.

2.6 		Tie-In Schedule

Together with the Site construction Schedule, CONTRACTOR SHALL submit a preliminary Tie-in and Shutdown Schedule.

Prior to CONTRACTOR's performance of any tie-in work, CONTRACTOR SHALL prepare and submit for COMPANY’s review and approval CONTRACTOR's schedule for the performance of such tie-ins.

The schedule SHALL be based on the CONTRACT Implementation Schedule and SHALL identify all systems and subsystems to be subject to tie-in or hook up.

In the event that the tie-in or hook-up is necessary to be carried out during complete or partial shutdown(s) of existing facilities the duration SHALL be as short as possible and SHALL not exceed the duration(s) estimated in the CONTRACTOR’s preliminary schedule.

2.7 	Completion and Handover Schedule

As the PROJECT nears Completion, COMPANY will advise CONTRACTOR of COMPANY's priorities for the completion of the WORK required under this CONTRACT.

Should such priorities differ from the completion dates or the sequence of activities shown on the CONTRACT Implementation Schedule then CONTRACTOR SHALL produce and submit to COMPANY for review a Completion and Handover Schedule.

Such schedule will specifically identify activities, quantities, manpower, materials and equipment required on a daily basis to achieve the orderly completion of the WORK in accordance with COMPANY's priorities.

The Completion and Handover Schedule SHALL be consistent with COMPANY's plans, schedules and procedures for operation of the facility.

Upon COMPANY's review of the Completion and Handover Schedule, CONTRACTOR SHALL conduct its activities in accordance therewith and such schedule SHALL have precedence over the applicable portions of the CONTRACT Implementation Schedule.

3.0 	REPORTING

3.1	Progress Reporting

During the performance under this CONTRACT, CONTRACTOR SHALL prepare and submit to COMPANY's Representative periodic progress reports on the actual progress of the WORK. Such reports SHALL be furnished in the form, number and manner and at the times required under this CONTRACT or by COMPANY’s Representative.  The progress reports described in this article SHALL serve to measure CONTRACTOR's progress and to record the status of CONTRACTOR's performance under the CONTRACT. The reports SHALL consist of the following:

- 	Weekly report with a look ahead;

- 	Monthly progress report with a look ahead.

3.2		Weekly Reports

On a weekly basis CONTRACTOR SHALL prepare and submit to COMPANY's Representative a weekly report on the progress of the work. A reporting week SHALL start on a Saturday and the last day SHALL be a Friday. The weekly report should be in COMPANY's Offices on-site two (2) days before the weekly meeting.

The reports SHALL contain the following information:

i-	Procurement Status Report:-

Full list of procurement deliverables identifying duration, planned dates and the progress and the status of CONTRACTOR furnished materials, with particular emphasis on fabricated and speciality items, and SHALL highlight areas of concern and areas where delays have, or are likely to occur.  The report SHALL also highlight CONTRACTOR's efforts to resolve or alleviate the effects of such concerns or delays.

The report SHALL also highlight equipment and materials shipped and SHALL include the following data:

-	Description of item shipped;

-	Approximate tonnage;

-	Date of shipment;

- 	Estimated date of arrival at site;

- 	The plan for the WORK to be done by the CONTRACTOR in the following two week period.

ii-	Construction Status Report:

The status of all CONTRACTOR's construction materials and equipment and all CONTRACTOR furnished permanent materials and equipment received at the CONSTRUCTION SITE.

The summary for construction materials and Equipment and permanent materials and equipment due but not received during the reporting period and SHALL contain CONTRACTOR's forecast of the requirements for the foregoing items.

The plan for the WORK to be done by the CONTRACTOR in the following two week period, including (pre-) commissioning and testing activities

Safety related items such as toolbox talks, surveys, safety statistics etc.

3.3	Weekly Progress Meetings

SITE Construction progress meetings will be held on a weekly basis, at times scheduled by COMPANY's Representative, to discuss the status of CONTRACTOR's progress on-site. CONTRACTOR’s Site Construction Manager SHALL attend such meetings and by CONTRACTOR's other cognisant personnel including CONTRACTOR's safety officer.

CONTRACTOR SHALL issue the approved Minutes of Meeting within two (2) days after the meeting.

The agenda for such meetings SHALL cover a review of on-site progress attained as per the Weekly Construction Status Report and a review of schedules and plans for future activities.

The agenda SHALL also cover the status of staffing, engineering, construction, (pre-) commissioning, testing, safety, equipment, material supply, current and anticipated difficulties, interface with other CONTRACTORs, claims for extras and other pertinent topics.

CONTRACTOR SHALL prepare the draft minutes of the meeting. The draft minutes SHALL be handed over to COMPANY’s Representative, on the day of the meeting, on floppy disk using the MS Word for Windows (latest version) software program and SHALL be reviewed and approved by COMPANY’s Representative. CONTRACTOR SHALL issue the approved Minutes of Meeting within two (2) days after the meeting.

3.4 	Monthly Progress Report

Within five (5) calendar days after the end of each month CONTRACTOR SHALL submit, together with the Monthly Payment Schedule, the Monthly Progress Report covering a review of CONTRACTOR's activities and progress made during the preceding month. Payment is conditional on receipt of the Monthly Progress Report together with the Monthly Payment Schedule. The Report SHALL as a minimum, contain:

- A management summary:

this summary SHALL inform the reader of all salient aspects of the PROJECT.

The summary SHALL be in such detail, that a reader, who is not involved in the day to day management of the PROJECT, will be fully up to date with the progress of the PROJECT. It SHALL be in such a format that it can be inserted directly in COMPANY's monthly activity report and SHALL contain the following items as a minimum: -

-	summary of man-hours worked, lost time accidents, near miss incidents, any significant environmental  spills, road traffic accident/incident, medical treatment  cases, safety initiatives and other safety topics.

Main CONTRACTOR and the SubCONTRACTOR’s figures should be submitted separately.

Appendix 6 shows a model format listing all monthly report requirements for guidance.

-	general progress of the WORK and a summary of accomplishments during the preceding month on all  major engineering, procurement, construction and  commissioning categories of WORK, consisting of a  narrative and photographs.

-	summary of areas of concern, identifying corrective  action being taken and potential impact on the performance of this CONTRACT.

-	status of engineering and procurement activities indicating progress to date and actions planned for the next month;

- 	summary of critical materials or equipment shortages.

- 	percentage of actual completion of the WORK compared with scheduled completion.

-	statement of the to-date amounts of CONTRACTOR's commitments, progress billings and progress payments  received.

-	summary of man-hours worked at the construction Sites within Syria.

-      change control register for schedules.

-	list of sub-CONTRACTORs employed over the month

(ii)	Tables showing the number of personnel by position or craft employed on the WORK, the number of such  personnel scheduled to be employed at that point of  CONTRACT performance;

(iii)	Graphs depicting the progress of WORK and percentage of actual completion of the WORK compared with scheduled completion. Graphs depicting the progress of each Execution Function and percentage of actual completion compared with scheduled completion.

(iv)	Ttrend Register.

(v) 	Numbers and items of construction equipment actually used at the construction sites and the construction equipment idle or inoperative during the reporting period.

(vi)	A copy of CONTRACTOR's barchart and network marked up with actual progress against planned progress, and actual milestone dates against planned milestone dates as defined in Exhibit “D”.

(vii) The Monthly Drawing Status List as further detailed in this schedule part B.4.

(viii)Design Status Report:

Full list of design deliverables, including drawing list per discipline, identifying duration, planned dates and the progress and status of preparation of CONTRACTOR prepared information and SHALL highlight areas where delays have or are likely to occur, other areas of concern and areas where COMPANY Representative’s resolution is required. The design status report will also include the progress reports against the action plans for follow-up on the Basic Design Review and HAZOP study.

(ix) 	Procurement Status Report:-

Full list of procurement deliverables identifying duration, planned dates and the progress and the status of CONTRACTOR furnished materials, with particular emphasis on fabricated and speciality items, and SHALL highlight areas of concern and areas where delays have, or are likely to occur.  The report SHALL also highlight CONTRACTOR's efforts to resolve or alleviate the effects of such concerns or delays.

The report SHALL also highlight equipment and materials shipped and SHALL include the following data:

-	Description of item shipped;

-	Approximate tonnage;

-	Date of shipment;

- 	Estimated date of arrival at site;

- 	The plan for the WORK to be done by the CONTRACTOR in the following two week period.

The monthly report SHALL be in sufficient detail to support and justify CONTRACTOR 's monthly invoice. The monthly invoice SHALL be submitted following approval by COMPANY’s Representative of the Payment Certificate, which is submitted together with the Monthly Report. Payment of the Monthly invoice that covers the progress for each month is based on the calculation of the value of the work done (VOWD) at the end of each calendar month and based on completion of milestones of each activity in accordance with the table in Exhibit C under title " Invoicing and Payment

3.5 	Management review meetings

COMPANY's representative and CONTRACTOR's representatives including Senior PROJECT management personnel plus key SubCONTRACTOR personnel SHALL meet COMPANY's management at times scheduled by COMPANY's representative, to review the status of CONTRACTOR's performance on this CONTRACT (if necessary).

4.0 	CONTRACTOR PREPARED INFORMATION

In CONTRACTOR's preparation of Information (as hereinafter defined), CONTRACTOR SHALL apply such skill, care and diligence as necessary to engineer the facilities so as to minimise engineering and construction rework (and thereby avoid costs and delays) and so as to produce Information which will lead to the construction of facilities which will be capable of efficient and convenient start-up, operation and maintenance.

All calculation books, drawings, diagrams, specifications, pamphlets, catalogues, literature, samples, data, printouts, certificates, parts lists, equipment lists, manuals, procedures, organisation charts and all like documents  (herein referred to as "Information") prepared by CONTRACTOR hereunder SHALL be available for review by COMPANY’s Representative at all reasonable times during development and be submitted promptly upon completion.

All such Information required to be submitted by CONTRACTOR for the review of COMPANY's Representative SHALL be prepared by and at the expense of CONTRACTOR and SHALL be processed in accordance with the requirements set forth herein. COMPANY Representative’s review of such Information submitted by CONTRACTOR SHALL not relieve CONTRACTOR of its responsibility for the correctness thereof or of its obligation to meet all the requirements under this CONTRACT.

CONTRACTOR SHALL not modify or deviate from Information reviewed by COMPANY's Representative without COMPANY’s Representative’s prior review of such modification or deviation. If required by COMPANY's Representative, CONTRACTOR SHALL modify such previously submitted Information to comply with PROJECT requirements.  COMPANY’s Representative’s decisions with respect to the adequacy and correctness of CONTRACTOR prepared Information SHALL be final and binding on CONTRACTOR.

In the preparation of Information hereunder, CONTRACTOR SHALL adopt the metric system of measurement units, (i.e. "Le Système international d'unitès -SI System"). The equivalent English (Imperial) unit SHALL be shown in parentheses after the metric unit.

All Information submitted by CONTRACTOR SHALL be certified by CONTRACTOR to be correct and representative of materials and equipment to be furnished or WORK to be performed by CONTRACTOR.

CONTRACTOR SHALL maintain a register showing the current status of all Information submittals made to COMPANY’s Representative and the status of all Information necessary for the successful execution of this CONTRACT. Copies of the register SHALL be provided to COMPANY's Representative on a monthly basis with the monthly report.

After the Commencement of the CONTRACT, CONTRACTOR SHALL submit to COMPANY's Representative a comprehensive listing of and schedule for the preparation of all Information CONTRACTOR proposes to submit to COMPANY's Representative.

CONTRACTOR's submission of Information for COMPANY’s Representative’s review SHALL be accomplished in accordance with the provisions below.

4.1 	Organisation Chart

CONTRACTOR SHALL, submit to COMPANY’s Representative an updated Organisation Chart showing CONTRACTOR’s organisation for the performance under the CONTRACT. The chart SHALL reflect peak manpower levels, SHALL include positions occupied or services performed by subCONTRACTORs, and SHALL indicate at least the following:

- 	day to day direct reporting relationships; and

- 	identification of Management, Craft Supervision , Engineering, Controls, Procurement and Commercial  Services personnel; and

- 	identification of operational personnel including a description of the person’s functions and the number of personnel assigned to each function. Separate identification SHALL be made for technical/professional and for clerical service personnel.

Changes in CONTRACTOR key staff SHALL only be implemented after written COMPANY approval has been obtained.  Failure to do so will be interpreted as a CONTRACTOR failure to fulfil his obligations.

4.2 	CONTRACTOR's Management and Supervision Personnel

CONTRACTOR SHALL provide a PROJECT Manager, as CONTRACTOR’s Representative during the full period of construction and commissioning activities.

CONTRACTOR SHALL provide as a minimum, Site management personnel from CONTRACTOR's own long-term staff during the full period of construction and commissioning activities for the following sole and unique job positions:

- 	Construction Manager & Quality Assurance/Quality Control Manager;

- 	PROJECT Engineers;

- 	Safety Officers;

- 	Materials Controller;

-	Planner;

- 	QA/QC specialists, with individual positions for welding radiography, civil work, rotating equipment, electrical, instrumentation, painting and coating;

- 	Commissioning / start-up engineers.

CONTRACTOR's PROJECT Engineer SHALL be an experienced competent engineer, and be able to address all technical matters, which may arise during on-Site construction. The PROJECT Engineer SHALL be in charge of maintaining the schedule for all pre-commissioning activities, co-ordinating all Vendor Representative activities, and the documentation of all precommissioning, commissioning and related matters.  The PROJECT Engineer SHALL be part of the design team during the basic design portion of CONTRACTOR's engineering WORK.  Upon completion of the basic design in CONTRACTOR's Office, the PROJECT Engineer SHALL be relocated to Site. The duration of his on-Site assignment SHALL be until issue of the Certificate of Provisional Acceptance of the WORK.

Supervisory personnel SHALL be provided from CONTRACTOR's own staff during the construction and commissioning activities carried out in their respective disciplines for the following sole and unique job positions:

- Pipe line supervisor .

- Mechanical / piping supervisor

- welding inspectors

- NDT inspectors

- Blasting supervisor (if applicable).

- Rout Survey Supervisor

- Material inspectors

- coating, painting and insulation inspectors

- hydro testing supervisor

- civil (building ,foundation  and steel structural ) inspectors

- Instruments/ control inspectors.

- Electrical inspectors

- Cathodic protection inspectors.

- Telecom inspectors

4.3 	Quality Control

After the CONTRACT Commencement, CONTRACTOR SHALL submit to COMPANY’s Representative for review, CONTRACTOR's Quality Plan covering the inspection and testing of all WORK to be performed under this CONTRACT whether at the Site or elsewhere.  The Quality Plan SHALL cover both off-site and on-site activities respectively and SHALL include, but SHALL not be limited to, a detailed description of each item or part of WORK to be inspected or tested, the nature and frequency of the inspection and testing, the type and size of samples to be taken, if any, the means of recording the inspection and testing data, the name and specific responsibility of any proposed testing or inspection agency and all other information necessary or required to fully describe the inspection and testing to be performed under  this CONTRACT. CONTRACTOR's Quality Plan as reviewed and modified by COMPANY SHALL be used for the inspection and testing of the WORK and SHALL be revised and re-submitted for COMPANY review if CONTRACTOR desires to change the sequence, method or nature of the inspection and testing or if the sequence, method or nature of the inspection and testing are not in accordance with the current CONTRACT Implementation Schedule and scope of WORK. Neither COMPANY's Representative's review of, or failure to review CONTRACTOR's Quality Plan SHALL relieve CONTRACTOR of his responsibility for the inspection, testing and performance of WORK required under this CONTRACT.

CONTRACTOR's responsibility for Quality Assurance and Quality Control during off-site and on-site WORK SHALL be with CONTRACTOR’s QA/QC Manager. This position SHALL be independent of CONTRACTOR's Line reporting, and SHALL have single line responsibility to CONTRACTOR's PROJECT Manager/PROJECT Director.

CONTRACTOR's QA/QC specialists on-site SHALL report to the QA/QC Manager independent of the on-site Construction Manager.

4.3.1 Quality Plan

CONTRACTOR’s Quality Plan SHALL be a CONTRACT Deliverable.

The Quality Plan SHALL incorporate the requirements of RFQ documents. It SHALL set out the specific quality practices, resources, responsibilities and activities relevant to all phases of the WORK, and SHALL result in documented evidence that the WORK is in accordance with the COMPANY’s Scope of Work and Specifications.

The Quality Plan SHALL include details of:

-	organisation & planning;

-	work instructions and records;

-	non-conformance, document and change control;

-	manufacturing control, critical hold and witness points;

-	completed item inspection and testing;

- corrective actions;

- test packs

all for each specific phase of the WORK, e.g. design, procurement, manufacturing, shipment, construction, commissioning etc.

CONTRACTOR SHALL incorporate all Quality activities into the Implementation Schedule.

CONTRACTOR SHALL maintain records giving evidence that the WORK complies with the CONTRACT requirements and that the Quality System is operating effectively.

CONTRACTOR SHALL be responsible for implementing its own audit and review activities assigned in the Implementation Schedule. The timings of audits and reviews SHALL be notified to COMPANY. COMPANY SHALL reserve the right to provide an observer to witness audits and reviews.

The following CONTRACTOR audits and reviews SHALL be performed as a minimum:

-	design quality assurance audit during the design phase;

-	hazardous operations audit towards the end of design;

-	interface control procedural audit during the design phase;

-	procurement audit;

-	manufacturing audit;

-	construction audit against Approved for Construction drawings.

The Quality Plan SHALL be registered under a controlled copy system and made available at each worksite for COMPANY and CONTRACTOR use.

4.4 Health, Safety and Environment (HSE) Plan

CONTRACTOR SHALL perform HSE activities in accordance with CONTRACTOR’s HSE Plan, using the resources, practices and controls described therein.

The HSE Plan SHALL be a CONTRACT Deliverable, submitted to COMPANY within sixty (60) days of CONTRACT’s commencement.

The HSE Plan SHALL be consistent with COMPANY’s HSE Scope of Work requirements and regulation as further set out in Exhibits “F” and SHALL be prepared specifically for the WORK, in recognition of the particular requirements of the WORK.

The HSE Plan SHALL contain at least the following:

-	CONTRACTOR’s Management HSE Policy statements;

-	CONTRACTOR’s Organisation showing responsibilities for HSE and their reporting relationships;

-	CONTRACTOR’s Systems and Procedures which it is intended to employ to meet the HSE objectives stated in the policy;

-	Schedule of HSE reviews/audits to monitor the application of procedures and the achievement of objectives;

-	HSE communications within the CONTRACTOR’s organisation;

-	HSE awareness programmes and training;

-	Incident and near-miss reporting and investigation/follow-up;

-	Procedures for assessment of SubCONTRACTOR’s HSE systems and compliance with HSE policies. SubCONTRACTOR’s HSE Plans should form part of CONTRACTOR’s HSE Plan (added as available);

-	HSE matrix listing all non-routine activities identified as hazardous activities warranting special actions and detailing contingency safeguarding actions.

a) 	The HSE Plan SHALL include a fully-developed three part tabulation listing the recognised Health, Safety and Environmental issues that may affect the WORK and future Operations and Maintenance, and detail the CONTRACTOR’s plan for mitigating the adverse effects of these issues. Details of discharged effluents, volumes and frequencies SHALL be supplied.

b) 	The HSE Plan SHALL include provisions, procedures and plans which recognise the need for concurrent COMPANY operations in the presence of certain CONTRACTOR’s construction activities, and activities by Others (e.g. overhead line CONTRACTOR) up to and beyond tie-in activities.

Such provisions, procedures and plans SHALL include, though not be limited to the detailing of Electrical Safety rules, Work Permit Systems, CONTRACTOR input to COMPANY/ CONTRACTOR/Other Concurrent Operations Planning, Authorised Switching Personnel etc. and SHALL give recognition and precedence to COMPANY’s obligation to perform all Work safely.

Planning of Concurrent Operations and tie-in WORK SHALL be performed in conjunction with COMPANY and Others (as necessary) and SHALL include time allowances and procedures for all necessary draining, purging, isolation and other making-safe operations, temporary access works, testing, radiography, Hydrotesting for whole or part-Systems affected by the WORK.

4.5	Transportation Plan

CONTRACTOR SHALL prepare for COMPANY review and audit a Transportation Plan, which SHALL be a CONTRACT Deliverable and SHALL be provided, to COMPANY for review.

The Transportation Plan SHALL demonstrate to the COMPANY’s satisfaction that the CONTRACTOR has provided adequate emphasis, consideration, action and contingency planning for the safe transportation and landing of the CONTRACT Hardware from the point of origin to the final installed position, which SHALL particularly include equipment requiring specialist transportation, temporary preservation, road escort and On-Site cranes and positioning equipment.

The Transportation Plan SHALL include specific contingency plans to ensure safe transport of the Hardware not only with respect to the safe intact delivery of the Hardware to the Worksites but also to provide enhanced safety measures to cater for the safety of third party road users encountering the Hardware in transit over public roads.

The Transportation Plan SHALL encompass all aspects of transportation including the country of origin, shipping and internal movement within the Syrian Arab Republic.

Key transportation activities SHALL be identified in the Implementation Schedule.

The Transportation Plan SHALL state the following as a minimum:

-	whether police escorts will be provided whilst in transit in either the country of origin and the Syrian Arab Republic;

-		whether movement will occur in restricted hours on public roads;

-		types of heavy vehicles and support vehicles required;

-		heavy lift plan featuring equipment, rigging, supervision, cranes & certification;

-		driver qualification and testing plans;

-		control and communication systems;

-		insurance provisions;

-		route surveys;

-		special precautions; and

- 		temporary access requirements.

Where no special arrangements are required in these (typical) areas, CONTRACTOR SHALL include a statement to that effect in the Transportation Plan.

4.6 	Schedule of CONTRACTOR's Submittals

CONTRACTOR SHALL submit to COMPANY all schedules, reports, invoices, timesheets, Information and all like documents and items (hereinafter in appendix 7 referred to as "Schedule of CONTRACTOR's Submittals") required under and at the times and frequencies required in this CONTRACT as applicable.

A register showing the status of the information submittals SHALL be included in the monthly progress report.

4.7 	Permit To Work (PTW) System.

CONTRACTOR SHALL adhere to COMPANY Concurrent Work Procedures (CONOPS) and use COMPANY Permit To Work system whenever working within existing COMPANY Facilities. (Refer to COMPANY HSE Requirements, Exhibit “F”).

CONTRACTOR SHALL prepare and use a permit to work system in line with COMPANY’s permit to work system, to cover the period from the start of the PROJECT until introduction of process media in the facilities. CONTRACTOR is fully responsible for the correct and safe operation of the newly installed facilities.

COMPANY's PTW system SHALL apply from the Introduction of Process Media.

Six (6) copies of the CONTRACTOR's proposed Permit To Work system SHALL be furnished to COMPANY's representative for approval.

After approval by COMPANY six (6) copies of the Permit To Work system have to be furnished to COMPANY representative prior to the date scheduled for the commencement of construction activities.

4.8 	Contract Documentation

CONTRACTOR SHALL prepare and submit to COMPANY's Representative the items of PROJECT Documentation described below. Such PROJECT Documentation SHALL be applicable to the facilities as actually constructed by CONTRACTOR and his subCONTRACTORs. PROJECT Documentation SHALL also incorporate appropriate data and information pertaining to the facilities which existed prior to the commencement of this CONTRACT.

Whenever possible PROJECT Documentation SHALL be prepared on A4 sheets with A3 drawing fold-outs, all assembled into hard cover post type binders not more than four inches thick.  The covers SHALL be imprinted with COMPANY's name and logo and appropriate titles.

CONTRACTOR SHALL prepare PROJECT Documentation in full co-ordination and co-operation with COMPANY's Representative and SHALL be subject to COMPANY's Representative's approval. Upon receipt of such approval, CONTRACTOR SHALL prepare and submit to COMPANY's Representative the required numbers of copies.

With respect to materials and equipment furnished by CONTRACTOR or its subCONTRACTORs or suppliers, CONTRACTOR SHALL be responsible for obtaining written permission from copyright owners for the use of data in the manner hereinafter provided. When copyright material is used, credit by footnote SHALL be given regarding the source. Unless expressly stated otherwise within the following sections, all PROJECT Documentation SHALL be submitted in the English language only.

4.8.1 Document Control

CONTRACTOR SHALL maintain a controlled copy system for the Document Register, which SHALL be a CONTRACT Deliverable.

The initial Document Register SHALL be provided for COMPANY information after CONTRACT’s commencement.

The Document Register SHALL record the current status of all drawings and documents in use by CONTRACTOR. The Register SHALL also record the current status of all drawings and documents issued under transmittals to COMPANY, and SHALL be used as such by COMPANY.

CONTRACTOR SHALL maintain the latest authorised and controlled copy of the Register on a licensed software programme and SHALL issue copies of the Register on floppy disks to COMPANY worksites at homs and On-Site

4.8.2 Calculation Books

CONTRACTOR SHALL assemble into Calculation Books copies on a technical discipline basis of all calculation sheets prepared by CONTRACTOR in the performance of the engineering design of the facilities. Calculations SHALL clearly identify any computer program used (Name of supplier, name of program, version number), input data, including source, and assumptions made.  CONTRACTOR SHALL provide a clear index for the Calculation books.

CONTRACTOR in-house developed computer programmes can only be used after documented validation and written COMPANY approval.

Copies of the Calculation Book SHALL be made available for the design review and six (6) such final books SHALL be furnished to COMPANY promptly on completion of the engineering design but in any case sixty (60) days prior to the planned date of start of precommissioning.

4.8.3 Manufacturer's Data Books

CONTRACTOR SHALL assemble into Manufacturer's Data Books all pertinent manufacturers’ technical data and information relating to all the various elements of the facilities as constructed by CONTRACTOR.  The data and information SHALL pertain to the facilities as a whole, to each major system, to each sub-system and every component down to the level  (for example) of washers and cotter pins. The Manufacturer’s Data Books SHALL commence with copy of CONTRACTOR’s Purchase Order (pricing information may be blanked out) followed by the manufacturer's equipment brochures, data sheets, certificates, parts lists and relevant "As Built" drawings. The information SHALL be presented on A4 size sheets, with A3 foldouts wherever possible. The certificates SHALL be copies of the test and performance certificates submitted to COMPANY’s Representative earlier during the procurement process.

The parts list SHALL be a comprehensive and complete listing of all material and equipment, which comprise the facilities. The parts list SHALL include item number, quantity of items, item name and description, manufacturer's name, brand name, model number and supplier’s name address and fax number. The parts list SHALL also include, sectional drawings identifying parts and information on the inter-changeability of parts and other information as required under the CONTRACT.

Should any Manufacturer's Data Books containing relevant "As Built" drawings be otherwise completed prior to the finalisation of the "As Built" drawings, then CONTRACTOR SHALL furnish sufficient copies of the final version of the "As Built" drawings and CONTRACTOR SHALL substitute the final version for the earlier versions in the books, also in case such books have already been handed over to COMPANY's Representative.

Three (3) sets of Manufacturer's Data Books SHALL be furnished to COMPANY's Representative sixty (60) days prior to the planned date of start of pre-commissioning. The Manufacturer’s Data Books SHALL be provided in hard copies with the name of the PROJECT and CONTRACT No. Printed on the spine and front of the binders.

The format and organisation of the Manufacturer's Data Books proposed by the CONTRACTOR should be subject to COMPANY's Representative's review and approval. As a minimum an index on alphabetical order and an index sorted by equipment number (down to instrument numbers) SHALL be provided.

4.8.4 Pre-Commissioning and Commissioning Manuals

CONTRACTOR SHALL prepare, or have prepared by specialist vendors, equipment and start-up manuals for all the facilities to be installed.

From these vendor manuals, CONTRACTOR SHALL prepare a Pre-commissioning and Commissioning Manuals describing CONTRACTOR’s proposals for CONTRACTOR's performance of pre-commissioning and commissioning WORK. The manuals SHALL show the sequence of events, SHALL describe in detail the various activities to be performed, SHALL stipulate the level of acceptable performance (operating envelope), SHALL list material, equipment and consumable items required and SHALL include samples of applicable check-out forms and tags. This documentation SHALL also include detailed system commissioning procedures and checklists.

The vendor manuals SHALL define each item/system of the plant in detail to support the design. These must be categorised under system groups. For example:

- 	vessel summary;

- 	exchanger summary;

- 	pump summary;

- 	switchgear summary;

- 	motor control summary;

- 	transformer summary;

-	U.P.S. summary;

- 	battery summary;

- 	turbine generator summary;

- 	emergency generator summary;

- 	compressor / blower summary;

- 	relief valve and orifice setting summary;

- 	instrument set point summary;

- 	flare system summary;

- 	fuel gas system summary;

- 	instrument and utility air system summary;

- 	utility water system summary;

- 	water supply system summary;

- 	diesel system summary;

- 	pig trap system summary;

- 	pipework system summary;

- 	miscellaneous equipment summary;

- 	cause and effect tables and summary.

These summaries are to be used to correlate between design and As-Built during the pre-commissioning and commissioning activities.

In addition CONTRACTOR SHALL produce a similar listing, which will illustrate the design and operating conditions of each item/system. This listing SHALL also include Acceptance Test Forms. These listings SHALL be provided to COMPANY on floppy disc in MS-WORD, EXCELL or ACCESS format.

Six (6) copies of the pre-commissioning and commissioning manuals SHALL be furnished to COMPANY for approval, sixty (60) days prior to the date scheduled for the commencement of the pre-commissioning or commissioning work.

After approval by COMPANY six (6) copies of the pre-commissioning and commissioning manuals have to be furnished to COMPANY representative prior to the date scheduled for the commencement of pre-commissioning or commissioning work.

Six (6) copies of the completed test/check sheets filled in with results of all precommissioning test/checks SHALL be furnished to COMPANY's Representative within 24 hours after the completion of these tests and in any case prior to the Introduction of process media.

Three (3) copies of the manual (in heavy binder) containing copies of the completed test/check sheets filled in with the results of all commissioning test/checks SHALL be furnished to COMPANY's Representative prior to the issue of the Certificate of Provisional Acceptance of the WORK.

4.8.5 Start-up Manual

CONTRACTOR SHALL prepare a Start-up Manual describing CONTRACTOR's recommendations for start-up and operation of the facilities. The manual SHALL describe in detail the sequence of start-up activities and the anticipated effects. The manual SHALL also describe the corrective actions to be taken in the event the anticipated effect does not occur or is not completely achieved. “Trouble Shooting" procedures SHALL also be provided. "Caution" and  "Warning" indications SHALL be clearly described and prominently displayed. Where such "Caution" and "Warning" indications require tags or notices to be affixed to the facilities then such tags and notices SHALL be prepared both in the Arabic and the English languages.

Six (6) copies of the start-up manual, including up-to-date basic design drawings, SHALL be furnished to COMPANY for approval, sixty (60) days prior to the scheduled start-up date of the facilities.

After approval by COMPANY six (6) copies of the start-up manual, including up-to-date basic design drawings, have to be furnished to COMPANY at least thirty (30) days prior to the date scheduled for the start up of the facilities.

4.8.6 "As Built" Drawings

CONTRACTOR SHALL provide an AutoCAD workstation and operator in Syria for the purposes of update of final “As-Built” drawings based on “red-blue” mark-ups as created during commissioning.

CONTRACTOR SHALL be fully responsible for assuring the quality of the “as-building” Deliverables which SHALL include the consistent and correct abstraction of “red-blue” data and the incorporation of the consequential changes required to other Engineering Documentation such that Integrity of Design is maintained consistently.

CONTRACTOR SHALL recognise the Value COMPANY places upon prompt receipt of correctly and consistently updated final “As-Builts”. The CONTRACTOR should also recognise that the issuance of Provisional Acceptance Certificate requires complete receipt of correctly and consistently updated final “As-Builts” prior to COMPANY release of the Certificate.

"As Built" drawings SHALL depict the facilities as actually constructed. The "As Built" drawings SHALL particularly show those portions of the facilities which CONTRACTOR constructe at variance with the details shown on the drawings issued by COMPANY or on the drawings prepared by CONTRACTOR and reviewed by COMPANY’s Representative.

The "As Built" drawings SHALL include, as applicable, pipeline right of way drawings showing the final as constructed alignment of the pipeline. Such "As Built” drawings SHALL be produced by CONTRACTOR on a continuous basis as the WORK proceeds but the final issue in all cases prior to the issue of the "Certificate of Provisional Acceptance of the WORK".  All "As Built" drawings SHALL be noted with a new revision number, includes those, which do not require modification from the previous revision.

One A1 and one A3 size heavy weight mylar reproducible, four (4) A3 size copies in binders and five (5) A1 copies of the "As Built" drawings as listed below SHALL be furnished to COMPANY.  As a minimum, the As Built drawings indicated, as such in the table below SHALL be provided within 1 week after the successful 72-hour test.

-	Process Flow Diagrams;

- 	Piping and Instrumentation Diagrams;

- 	Plot plans;

- 	Electrical One line diagrams;

- 	Instrument Hook-up Drawings;

- 	Instrument Cause and Effect Schedules;

- 	Instruments Connecting Diagrams;

- 	Shutdown System Drawings;

- 	Equipment Plotplans;

- 	Key Plans;

-	Hazardous Area Drawings;

- 	Pipe lines Routing Drawings;

- 	Functional Logic Diagrams.

-	Detailed design drawings as per schedule B, Engineering Documents.

CONTRACTOR SHALL prepare all the "As Built" drawings on the AutoCAD system (Version 14) and SHALL provide two copies of the complete as-built set on 3.5” floppies and on CD-ROM. A soft copy of the drawing list SHALL also be provided.

4.8.7 Operation and Maintenance Manuals

The Operation Manuals and Maintenance Manuals SHALL be prepared by CONTRACTOR utilising to a large extent information prepared by CONTRACTOR for data books and manuals. The operating manual will contain detailed start-up instructions; during the commissioning these procedures will be used to start-up the facility.

Six (6) sets of the Operation manuals and Maintenance manuals SHALL be furnished to COMPANY thirty (30) days prior to the planned date of start up.

Two (2) copies of the text of Operation manuals and Maintenance Manuals SHALL be furnished to COMPANY on a floppy disk in MS-WORD latest version.

The operating manuals SHALL be structured as self-contained step by step procedures to facilitate ease of understanding by COMPANY operators (and should not be confused with the commissioning and start-up manuals). The maintenance manuals SHALL include a maintenance plan in a format as already developed by COMPANY, a facility register for all maintainable items and maintenance task sheets.

CONTRACTOR SHALL prepare a drawing showing a 5-year running maintenance programme, based on vendor recommendation and good industry practice. For every maintenance activity CONTRACTOR will indicate required frequency, consequences of late or no maintenance and basis for suggested frequency. The drawing and the list will be included in the maintenance manual.

4.9 	Drawings

For the purpose of this article, the term "drawings" SHALL include but SHALL not be limited to Process Flow Diagrams (PFD), Piping and Instrumentation Drawings (P&ID), design, detail, fabrication, assembly, erection, setting, working, schedule and manufacturer's drawings, plot plans, bird's eye view of facilities, piping, wiring and control diagrams, specifications, equipment lists, vendor lists, parts lists, printouts, cuts from or entire catalogues, pamphlets and descriptive literature required under this CONTRACT or  required by COMPANY's Representative to demonstrate  CONTRACTOR's plans for the engineering, procurement,  manufacture, fabrication, shipment, assembly, installation,  erection, construction and commissioning of materials and equipment or where required to demonstrate CONTRACTOR's plans  for the performance under this CONTRACT

Drawings made on AutoCAD will, when practical, be a maximum A3 size. All marking and lettering will be easily readable in this format. A3 format drawings will be photocopyable without loss of quality. The maximum drawing size will be A1. A1/3 drawings will be provided on heavy weight Mylar material.

Main process streams SHALL run from left to right on the PFD's and the P&ID's; the P&ID's SHALL also reflect the trip settings and the relief valve settings and orifices.

On piping drawings, pipe of two-(2) inch diameter or larger SHALL be represented by double lines and on P&ID's no more than one (1) major vessel SHALL be shown per sheet.  Whenever possible printed material SHALL be submitted on A4 sheets with A3 foldouts.  CONTRACTOR's drawing submittals SHALL include multi-coloured plasticised bird's eye view drawings.

CONTRACTOR SHALL submit the following copies of all drawings to COMPANY to obtain permission to proceed with manufacture, fabrication, shipment, assembly, installation, erection, construction or commissioning:

i.   	at all stages of the CONTRACT, five (5) A3 size and two  (2) copies A1 size of each drawing for COMPANY's in-house review, which fall in the following categories:

- 	Process Flow Diagrams;

- 	Piping and Instrument Diagrams;

- 	Electrical Connecting Diagrams;

- 	Instrument Hook-up Drawings;

- 	Instrument Cause and Effect Schedules;

-	Instruments Connecting Diagrams;

-	Shut Down System Drawings;

- 	EquipmentPlotplans;

- 	Key plans;

- 	Hazardous area drawings;

- 	Pipe line Routing Drawings;

- 	Functional Logic Diagrams.

These categories of drawings form the basic design drawings and are to be considered the minimum of drawings to be subject to review by COMPANY.

Two (2) A1 size set and six (6) A3 size sets of basic design drawings will be made available by CONTRACTOR for the HAZOP review after the completion of the basic design.

ii.  	The issue of the above drawings as "As-Builts" is subject to clause 4.8.6 of this Schedule.

iii. 	Detailed construction drawings other than as listed in point i. above, are to be submitted as three (3) copies in A1 size, two (2) copies in A3 size and one (1) A3 reproducible.

Drawings SHALL be complete and detailed and SHALL be checked and co-ordinated by CONTRACTOR with all disciplines involved before they are submitted to COMPANY's Representative. Each drawing SHALL bear CONTRACTOR's stamp of approval as evidence of such checking and co-ordination and those drawings submitted without such stamp of approval may be returned to CONTRACTOR for re-submission.

Where drawings submitted to COMPANY contain more than five errors, omissions or holds, they are considered unsuitable for submission to COMPANY and SHALL be re-submitted to COMPANY for approval after correction by CONTRACTOR.

The title block on each drawing SHALL display the following:

-	COMPANY's name and CONTRACT number;

- 	Number and title of drawing;

- 	Date of drawing and drawing revision;

- 	Name of CONTRACTOR (and subCONTRACTOR, if applicable);

- 	Name of PROJECT facility; and

- 	Clear identification of contents and location.

CONTRACTOR SHALL submit drawings sufficiently in advance of manufacture, fabrication, shipment, assembly, installation, erection, construction or commissioning to review and appropriate action by COMPANY's Representative.

After the date CONTRACT commencement, COMPANY's Representative and CONTRACTOR SHALL agree on a procedure for the submission and review of drawings. Such procedures will cover CONTRACTOR's submission of original, revised and re-submitted drawings, COMPANY’s Representative’s review and return of drawings, CONTRACTOR’s incorporation of COMPANY's Representative's comments, and the maintenance of registers recording the status of such submissions and returns.  The procedure will also include review categories which will stipulate the extent of COMPANY’s Representative's permission for CONTRACTOR to proceed with the manufacture, fabrication, shipment, assembly, installation, erection, construction or pre-commissioning covered by the applicable drawings.

CONTRACTOR SHALL prepare and submit a drawing status list at monthly time intervals showing drawing title, location, number and revision number, and drawing status in accordance with the submission and review procedure. This Status List is to be submitted with the Monthly Payment Schedule.

COMPANY's Representative's permission to proceed SHALL not constitute approval of design details, calculations, analyses, test methods or materials developed or selected by CONTRACTOR and SHALL not relieve CONTRACTOR from full compliance with CONTRACTual obligations.  Nor SHALL COMPANY’s Representative’s review of CONTRACTOR's drawings be held to relieve CONTRACTOR of any of its obligations to meet all requirements of this CONTRACT or relieve CONTRACTOR of the responsibility for the corrections of such drawings.  CONTRACTOR SHALL at its expense, make any changes in the design which are necessary to make the WORK conform to the provisions under this CONTRACT.

When drawings have been satisfactorily completed, CONTRACTOR SHALL carry out the procurement, manufacture, fabrication, shipment, assembly, installation, erection, construction and commissioning, as applicable, in accordance therewith and SHALL make no further changes therein except upon written instruction from COMPANY's Representative.

CONTRACTOR SHALL be responsible for and SHALL bear all costs of damages which may result from the procuring of any material or equipment or from proceeding with any part of the WORK prior to receiving permission to proceed from COMPANY's Representative.

CONTRACTOR SHALL maintain at the Site and other places where WORK is being performed, at all times when WORK is in progress, a complete set of relevant and up to date drawings.

4.10Samples.

Where samples of CONTRACTOR-furnished materials or equipment are required by this CONTRACT or required by COMPANY’s Representative, four (4) such samples SHALL be submitted by CONTRACTOR. Such submittals SHALL be made thirty (30) calendar days prior to the time that the materials or equipment represented by such samples are needed for incorporation into any WORK.

Samples SHALL be subject to review and materials or equipment represented by such samples SHALL not be manufactured, delivered or incorporated into any WORK without such review.

Each sample SHALL bear a label showing CONTRACTOR's name, subCONTRACTOR’s name, if applicable, PROJECT name, place of origin, name of the item, manufacturer's name, brand name, model number, supplier's name, reference to the appropriate drawing number, specifications section and paragraph number, and date of submittal, all as applicable.

Review of a sample SHALL be only for the characteristics or use named in such review and SHALL not be construed to change or modify any CONTRACTual requirement.

In the event CONTRACTOR proposes the substitution of an alternative item for an item specified in this CONTRACT, CONTRACTOR SHALL, if so required by COMPANY's Representative, submit samples of the proposed alternative item. The substitution of alternative items, where permitted by COMPANY's Representative, SHALL be accomplished in accordance with the applicable provisions of Exhibits.

Materials and equipment incorporated into the WORK SHALL match the approved samples. Failure of any material to pass the specified tests may be sufficient cause for refusal to consider under this CONTRACT any further samples of the same brand or make of that material.

COMPANY's Representative SHALL disapprove any material or equipment, which previously has proved unsatisfactory in service, whether on this CONTRACT or elsewhere.  When tests are required, only one test of each sample proposed for use will be made at the expense of COMPANY. Samples which do not meet the requirements of Exhibits will be rejected. Re-testing of additional samples will be done by COMPANY’s Representative at the expense of CONTRACTOR.

Samples, which have been reviewed, may, at COMPANY's Representative's option, be returned to CONTRACTOR for incorporation into the WORK.