PEA APPENDIX 4

SPARE PARTS DOCUMENTATION AND PURCHASING

The action required completing the SPIR Form and its continuation sheet, if necessary, is described in the following parts:

Part 1	covers sections to be completed by the Contractor prior to issue of the SPIR Forms.

Part 2	covers Columns 1 to 12 inclusive, 19 and 20. It describes information to be provided by the equipment manufacturer (Vendor)

Part 3	covers Columns 13, 14, 15, 18 and Block 21. It describes the action to be taken either individually or jointly by the Contractor and Operating Division of Company (SPC).

Part 4	covers Columns 16, 17 and Authority Block 22. It describes the action to be taken by the party/parties usually nominated in the Project Specification, normally Operation Division.

- DETAILED INSTRUCTIONS FOR COMPLETION OF PART 1

It is recommended that the Contractor prior to submission to Vendor complete the sections.

SPIR No.:	This number will be allocated by Contractor on a sequential basis as follows:

# Mechanical Equipment	-	S100 Onwards

Electrical Equipment	-	S500 Onwards

Instrumentation		-	S700 Onwards

## Subject:	Brief description of equipment

Manufacturer:	Name of prime manufacturer (i.e. manufacturer with whom Purchase Order is placed) (Vendor).

Date:	Date of issue of SPIR Form to Vendor.

Project/Plant:	Name of project to which equipment on SPIR Form refers.

Consignee:	Name of Company e.g. Syrian Petroleum Company.

Engineering by:	Name of Contractor undertaking procurement of spares.

2	DETAILED INSTRUCTIONS FOR COMPILATION OF PART 2.

To be completed by the equipment manufacturer in the following sequence:

Column 1  - 	Enter the same equipment registration number(s) or tag number(s) for each piece of equipment as stated in requisitions and/or purchase orders. (Tag Nos. are much preferred)

Column 2  - 	Manufacturer's model, type or other positive identification reference of the equipment ordered.

Column 3  - 	Manufacturer's serial number or other control reference of the equipment/instruments as being supplied

Column 4  - 	Total number of pieces of identical equipment listed in columns 1 to 3 and 6.

Column 6  - 	Purchasing COMPANY's order reference number.

Column 8  -	Describe all parts in English language. List all parts, which should be carried in stock for normal operation and also list slow-wearing parts.

If an item is interchangeable between two or more units it should be listed once only.

Column 9  -	For each part entered in Column 8 enter the drawing number or reference number.

Note:	The Manufacturer should attach these drawings to the SPIR.

Column 10- 	Enter the reference numbers/letters or other information which identifies each part.

Interchangeability with identical parts within the Manufacturer’s range should be indicated.

Owing to the wide variety of systems in use for identification of parts, it is impossible to lay down firm rules for completing these columns. Manufacturer’s should give whatever identification system they use to positively identify parts and to show interchangeability with existing equipment.

Manufacturer’s final cross-sectional drawings, workshop drawings and real part numbers may not always be available in the early stage of manufacture. This may cause delays in timely preparation of manufacturer’s recommendation for initial spare parts* in column 12 and subsequent ordering of same.

If delays are unacceptable, it is recommended that reference is made to manufacturer’s recommendation, which is readily available such as pamphlets, brochures, exploded views, typical drawings of similar equipment.

*	Manufacturers are advised that “initial spare parts” are defined as follow:

“Initial spare parts are safeguard the operation of equipment during the running in and starting up period, and the quantity should be adequate to cover the period until the arrival of spare parts for normal operation. Latter period should for practical purposed be taken as approximately one year.

Initial spare parts must therefore be ordered at such an early date that ideally they will arrive at site at the same time as the parent equipment, but in any case prior to start up.”

Column 11- 	Enter material specifications in terms of full international standards and accepted conventions, not manufacturer's or sub-manufacturer's references.

Column 5  - 	For each equipment or group of identical equipment, enter in the appropriate space opposite each part the quantity of the described parts fitted in each piece of equipment or instrumentation.

Column 7  -	Enter the total number of identical parts in all equipment specified. In the case of identical units multiply the quantity in Column 5 by the number of units given in Column 4.

Column 12- 	Enter the manufacturer’s recommended quantities of initial spare parts, which are likely to be needed during start up and the first year of normal operation.

Column 19  -	Enter the approximate ex-works price per piece of each part in the currency shown at the top of column.

Column 20  -	Enter the original manufacturer’s identification numbers of all items of third party manufacture “bought out” items such as ball bearings, oil and mechanical seals, couplings.

Note:	Manufacturers must not complete Columns 13 to 18 inclusive nor Blocks 21 and 22.

- DETAILED INSTRUCTIONS FOR COMPLETION OF PART 3

It is recommended that the columns are completed by the Contractor and/or the Operating Division of Company in the following sequence:

Column 18  	For instrumentation this column should be left blank. Other equipment and its spare parts should be classified in accordance with the guidance given in the attached ANNEX-1.

# Equipment Classification

Equipment meeting the “vital” definition should be coded by V.

Equipment meeting the “essential” definition should be coded by E

Equipment meeting the “auxiliary” definition should be coded by A

### Spare Parts Classification

Parts identified as “consumable” should be coded C.

Parts identified as “replacement” should be coded R.

Parts identified as “insurance items” should be coded I.

Column 13* (for initial spares only):

Having duly scrutinized the manufacturer’s recommendation in column 12, enter the quantities of initial spare parts recommended.

Although primarily intended to cover the start up period and early stages of normal operation, the quantities entered here should be integrated with the parts for normal operation, i.e. Column 15 will represent the total recommended number of spare parts to be ordered.

Column 14*	(for normal spares only):

If applicable to the project, enter the quantities of spare parts for normal operation.

Column 15*	(for normal spares only):

In Column 15, the Operating Division finally recommends the quantity of each part listed under Column 8, which is required for start up and normal operation, taking into account the existing stock position and consumption history.

For instrument parts Column 15 will indicate the quantities required as initial spare parts and those required for the early stage of operation.

*	To avoid any misunderstanding by users of the completed SPIR Forms, it is emphasized that the quantities calculated and entered in Columns 13, 14 and 15 must not be ordered, since they represent only recommendations/technical approval.

Note:	Purchasing must not proceed until the authority to order is given by the party who controls the project budget expenditure. This authority must explicitly be given by completing Block 22, see Part 3.

Block 21  -	Enter the date by, which spare parts must be available for use on site. Generally known as the “required on site” date, this should be consistent with the actual and latest known start up and commissioning period as advised by the project leader.

Note:	At this stage it will be helpful for users to know that the form now contains final recommendations. This fact should be clearly indicated, as should the date of completion.

#### DETAILED INSTRUCTIONS FOR COMPLETION OF PART 4

It is recommended that the parties indicated below to complete the columns:

##### Column 16  -	The parties for authorizing expenditure (or his delegate) enters in this Column the exact quantities to be ordered.

###### Authority Block 22

This block must give the name of the Company or other authority who is authorizing the purchase of the quantities entered in Column 16.

Column 17  -	This Column should be left blank.